## Slide 1: The National Declassification Center
Releasing All We Can,
Protecting What We Must
Public Interest Declassification Board
NDC Project Update
April 22, 2010
Notes: The National Declassification Center
Releasing All We Can,
Protecting What We Must
Public Interest Declassification Board
NDC Project Update
April 22, 2010

## Slide 2
On 4 January 2010, less than a week after the President signed EO 13526, NARA established the NDC at Archives II at College Park.
NARA entered into a partnership with the Lean Six Sigma Program (LSS) under the Department of Defense’s Deputy Chief Management Officer (DCMO) to conduct a detailed Business Process Re-engineering project.
NARA is currently in the process of:
  Reconfiguring existing workspace at Archives II to accommodate additional agency reviewers, and support review of special media records.
  Improving NDC declassification processes by making changes that will reduce backlogs and ensure quality reviews, without the need for multiple re-reviews.
  Creating a library of approved declassification guides.
  Developing equity recognition training and certification for all reviewers.
Notes: Establishing the NDC
On 4 January 2010, less than a week after the President signed EO 13526, NARA established the NDC at Archives II at College Park.
NARA entered into a partnership with the Lean Six Sigma Program (LSS) under the Department of Defense’s Deputy Chief Management Officer (DCMO) to conduct a detailed Business Process Re-engineering project.
NARA is currently in the process of:
  Reconfiguring existing workspace at Archives II to accommodate additional agency reviewers, and support review of special media records.
  Improving NDC declassification processes by making changes that will reduce backlogs and ensure quality reviews, without the need for multiple re-reviews.
  Creating a library of approved declassification guides.
  Developing equity recognition training and certification for all reviewers.

## Slide 3: What Will the NDC DO?
Develop processes that will effectively integrate, coordinate and support interagency declassification review and interagency referral of equities in permanent historical and transferred Presidential records
Consolidate approved declassification guidelines into a library that can be used by authorized reviewers in the NDC
Develop instructional and automated declassification and equity recognition training programs
Support equity agency review of, and process classified special media, electronic and textual records for declassification and public release
Notes: What Will the NDC DO?
Develop processes that will effectively integrate, coordinate and support interagency declassification review and interagency referral of equities in permanent historical and transferred Presidential records
Consolidate approved declassification guidelines into a library that can be used by authorized reviewers in the NDC
Develop instructional and automated declassification and equity recognition training programs
Support equity agency review of, and process classified special media, electronic and textual records for declassification and public release

## Slide 4: NDC Processes
Through our LSS partnership, NARA established an interagency PMT that is working to improve and streamline NDC processes that will:
  Ensure the standardization and collection of declassification review related data between Federal agencies and the NDC.
  Develop a prioritization plan to focus declassification efforts on the records of the most interest to the public.
  Establish a Quality Assurance program that allows the NDC to check the quality of review and eliminate the 408 million page backlog at NARA.
  Create an interagency referral program that facilitates the review of Federal and Presidential records.
Notes: NDC Processes
Through our LSS partnership, NARA established an interagency PMT that is working to improve and streamline NDC processes that will:
  Ensure the standardization and collection of declassification review related data between Federal agencies and the NDC.
  Develop a prioritization plan to focus declassification efforts on the records of the most interest to the public.
  Establish a Quality Assurance program that allows the NDC to check the quality of review and eliminate the 408 million page backlog at NARA.
  Create an interagency referral program that facilitates the review of Federal and Presidential records.

## Slide 5: NDC Processes
The NDC is facing:
Scope: 408M pages of classified records over 25 years old and accessioned to NARA.
Classified Pages Accessioned Annually: 15M pages
Classified Pages Available to the Public Annually: 11M pages
Growth Rate of the Backlog: +4M pages per year
Summary: With the current level of resources in both the agencies and NARA, the backlog would NEVER clear using the current processes.
Notes: NDC Processes
The NDC is facing:
Scope: 408M pages of classified records over 25 years old and accessioned to NARA.
Classified Pages Accessioned Annually: 15M pages
Classified Pages Available to the Public Annually: 11M pages
Growth Rate of the Backlog: +4M pages per year
Summary: With the current level of resources in both the agencies and NARA, the backlog would NEVER clear using the current processes.

## Slide 6: NDC Processes
Status:
Created process maps for the agencies 25 Year Automatic Declassification Processes and NARA’s declassification process at College Park, MD
Identified 4 key areas of the NARA process that contribute to the long cycle time.
Current total cycle time for the process at NARA is 3-7 years; the oldest accessioned records in the backlog were accessioned in 1959.
Next Steps:
Focusing on improving four areas in the As-Is Process Map where long cycle times have been identified to make this process more efficient
Developing Draft To-Be Process and running pilots on the improved process
Identified options to process 120M pages a year to meet the date of December 31, 2013 (10X increase in throughput)
Notes: NDC Processes
Status:
Created process maps for the agencies 25 Year Automatic Declassification Processes and NARA’s declassification process at College Park, MD
Identified 4 key areas of the NARA process that contribute to the long cycle time.
Current total cycle time for the process at NARA is 3-7 years; the oldest accessioned records in the backlog were accessioned in 1959.
Next Steps:
Focusing on improving four areas in the As-Is Process Map where long cycle times have been identified to make this process more efficient
Developing Draft To-Be Process and running pilots on the improved process
Identified options to process 120M pages a year to meet the date of December 31, 2013 (10X increase in throughput)

## Slide 7: NDC Processes
Process Changes Under Discussion:
Make changes to facilitate completing archival processing after declassification instead of during.
Insert decision points into the Quality Assurance (QA) process so records can bypass some or all of the QA steps.
Embrace a risk management approach by instituting a sample review process in QA, focusing QA review on high risk collections.
Expanding the Interagency Referral Center to allow more agencies access to their referrals
Notes: NDC Processes
Process Changes Under Discussion:
Make changes to facilitate completing archival processing after declassification instead of during.
Insert decision points into the Quality Assurance (QA) process so records can bypass some or all of the QA steps.
Embrace a risk management approach by instituting a sample review process in QA, focusing QA review on high risk collections.
Expanding the Interagency Referral Center to allow more agencies access to their referrals

## Slide 8: BPR of the NDC
In October 2009, NARA began a BPR of NDC declassification, referral and processing procedures. The BPR will consist of five phases with an estimated completion date of May 2010.
  Phase I – Define (completed)
    Identify stakeholders
    Define scope and activities
    Phase I completed October 30, 2009
  Phase II – Measure (completed)
    Examine As-Is processes (both internal NARA and outside agencies)
    Identify measures required to determine success
    Phase II completed December 18, 2009
  Phase III – Analyze (completed)
    Analyze data gathered
    Phase II completed date January 29, 2010
  Phase IV – Improve (In Progress)
    Develop To-Be Processes
    Estimated completion date April 26, 2010
  Phase V – Control (In Progress)
    Implement and monitor process changes
    Estimated completion date May 28, 2010
Notes: BPR of the NDC
In October 2009, NARA began a BPR of NDC declassification, referral and processing procedures. The BPR will consist of five phases with an estimated completion date of May 2010.
  Phase I – Define (completed)
    Identify stakeholders
    Define scope and activities
    Phase I completed October 30, 2009
  Phase II – Measure (completed)
    Examine As-Is processes (both internal NARA and outside agencies)
    Identify measures required to determine success
    Phase II completed December 18, 2009
  Phase III – Analyze (completed)
    Analyze data gathered
    Phase II completed date January 29, 2010
  Phase IV – Improve (In Progress)
    Develop To-Be Processes
    Estimated completion date April 26, 2010
  Phase V – Control (In Progress)
    Implement and monitor process changes
    Estimated completion date May 28, 2010

## Slide 9: Consolidate Declassification Guides
The NDC staff is testing a newly built Declassification Guide Web Application (DGWA) to:
  Centralize all equity recognition guides and make them accessible to reviewers working in the NDC.
  Establish a library of declassification guides that can be used by reviewers in the NDC to ensure they have access to the most up to date versions of their agency’s guidelines.
Notes: Consolidate Declassification Guides
The NDC staff is testing a newly built Declassification Guide Web Application (DGWA) to:
  Centralize all equity recognition guides and make them accessible to reviewers working in the NDC.
  Establish a library of declassification guides that can be used by reviewers in the NDC to ensure they have access to the most up to date versions of their agency’s guidelines.

## Slide 10: Training Programs
Currently the NDC staff is planning:
  May 24-25, 2010 – A two day equity recognition training program to instruct reviewers on equities in the NARA backlog.
  Spring 2011 – An intensive 4 or 5 day interagency equity recognition training conference.
  In development:
    7 Declassification training courses
      - 4 Web based courses
      - 3 Instructor led courses
    One day course: Managing the Lifecycle of National Security Information Through Effective Records Management: A Course for Agency Records Managers and Security Specialists
Notes: Training Programs
Currently the NDC staff is planning:
  May 24-25, 2010 – A two day equity recognition training program to instruct reviewers on equities in the NARA backlog.
  Spring 2011 – An intensive 4 or 5 day interagency equity recognition training conference.
  In development:
    7 Declassification training courses
      - 4 Web based courses
      - 3 Instructor led courses
    One day course: Managing the Lifecycle of National Security Information Through Effective Records Management: A Course for Agency Records Managers and Security Specialists

## Slide 11: Special Media Records
NARA staff have completed preservation actions on 95% of classified special media records in NARA custody. These records are in a format that can be reviewed by the equity agencies.
NARA has established a classified special media lab and will soon be able to support:
  Agency review of their classified equities in multiple special media formats.
  Redaction and public release of declassified special media records.
Notes: Special Media Records
NARA staff have completed preservation actions on 95% of classified special media records in NARA custody. These records are in a format that can be reviewed by the equity agencies.
NARA has established a classified special media lab and will soon be able to support:
  Agency review of their classified equities in multiple special media formats.
  Redaction and public release of declassified special media records.

## Slide 12: Prioritization
NARA is working on a Prioritization Plan that will:
  Establish priorities for declassification and interagency referral review.
  Incorporate public and historical community input when establishing NDC declassification, referral and processing priorities.
  Make referrals in transferred Presidential records a top NDC priority.
The plan will be based on a matrix that takes into account public interest in the records, and expected volume of records that can be declassified through the NDC.
Notes: Prioritization
NARA is working on a Prioritization Plan that will:
  Establish priorities for declassification and interagency referral review.
  Incorporate public and historical community input when establishing NDC declassification, referral and processing priorities.
  Make referrals in transferred Presidential records a top NDC priority.
The plan will be based on a matrix that takes into account public interest in the records, and expected volume of records that can be declassified through the NDC.

## Slide 13: The NDC Moving Forward
NARA developed a Strategic Communications Plan to ensure communication with all NDC customers is coordinated and up to date. Elements of the plan include:
  Creating the NDC website (www.archives.gov/declassification) which includes
    An overview of the NDC and its role
    Links to resources related to the EO and declassification
    A page that will list newly declassified records as they are available to the public
    A link to the NDC e-mail box for questions and comments
  Conducting meetings with agencies and the public to receive input and feedback on the operation of the NDC.
  Briefing agencies on the NDC and changes to the process
Notes: The NDC Moving Forward
NARA developed a Strategic Communications Plan to ensure communication with all NDC customers is coordinated and up to date. Elements of the plan include:
  Creating the NDC website (www.archives.gov/declassification) which includes
    An overview of the NDC and its role
    Links to resources related to the EO and declassification
    A page that will list newly declassified records as they are available to the public
    A link to the NDC e-mail box for questions and comments
  Conducting meetings with agencies and the public to receive input and feedback on the operation of the NDC.
  Briefing agencies on the NDC and changes to the process

## Slide 14: The NDC Moving Forward
Implement changes to the NDC processes developed through the BPR.
Standardize practices across agencies as determined by the BPR.
Additional NDC Process Improvement Projects
  IT System Design to support improved NDC processes
  BPR to improve and develop processes for interagency declassification review and processing of special media and electronic records
  BPR to improve the NARA FOIA/MDR process for classified Federal records
Notes: The NDC Moving Forward
Implement changes to the NDC processes developed through the BPR.
Standardize practices across agencies as determined by the BPR.
Additional NDC Process Improvement Projects
  IT System Design to support improved NDC processes
  BPR to improve and develop processes for interagency declassification review and processing of special media and electronic records
  BPR to improve the NARA FOIA/MDR process for classified Federal records