## PMRS 2.0 Reqts
REQUIREMENTS | [9 empty] | DESIGN | DEVELOPMENT | VERIFICATION |  |  |  | DEPLOYMENT PREPARATION
Req # | Requirement Text | Type | Category | Feature | Req Priority | Status | Target Release | Source | Notes | Element | Iteration | Verification Method | Verification Test Case / Step | Verification Status | Verification Criteria | UAT Test Case | UAT Status | Validation Criteria
1 | National Archives and Records Administration (NARA) users shall be able to perform analysis on data for NARA systems. | Business | N/A | Data Analysis | Must | Approved |  | Stakeholder Discussions
1.1 | The solution shall provide the capability for a user to perform ad hoc calculations. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.11 | Ad-hoc calculations are calculations that you can create and update as you work with a field on a row or column of data in the view, to create and see "what if" scenarios.
1.2 | The solution shall provide the capability for a user to filter data on multiple variables. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.12
1.3 | The solution shall provide the capability for a user to filter data on multiple data elements/attributes. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.12
1.4 | The solution shall provide the capability for a user to record the summary of numeric data as a stock variable. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.21 | A stock variable is a quantity which is measurable at a particular point of time.
1.5 | When summarizing numeric data, the solution shall provide the capability to display the summary of the most recent value (stock variable). | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.21 | A stock variable is a quantity which is measurable at a particular point of time
1.6 | The solution shall provide the capability for a user to record the summary of numeric data as a flow variable. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.21 | A flow variable is a quantity which is measured with reference to a period of time.
1.7 | When summarizing numeric data, the solution shall provide the capability to display the sum of the data for a given time period (flow variable). | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.21 | A flow variable is a quantity which is measured with reference to a period of time.
1.8 | The solution shall provide the capability for a user to display selected measures. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.4.1 | Many PMRS multi-dimensional reports show a variety measures: number of, percent of, holdings in cu. ft., holdings in pages, start-of-year holdings, etc. Users want to be able to hide the measures that don't interest them, in order to de-clutter the view.
1.9 | The solution shall provide the capability for a user to hide selected measures. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.4.1 | Many PMRS multi-dimensional reports show a variety measures: number of, percent of, holdings in cu. ft., holdings in pages, start-of-year holdings, etc. Users want to be able to hide the measures that don't interest them, in order to de-clutter the view.
1.1 | The solution shall provide the capability for a user to display two or more measures simultaneously. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.4.2 | Users want to be able to compare measures in a display, such as a seeing the number of respondents to a survey, the number of happy respondents, and the % happy.
1.11 | The solution shall provide the capability for a user to view the values of data points on graphical displays. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 1.4.4 | The user should be able to see the data values underneath an object by mousing over the data point.
1.12 | The solution shall provide the capability for a user to swap between text and graphical displays of the same data. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.6.1
1.13 | The solution shall provide the capability for a user to switch between types of graphical displays. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.6.2 | This supports the capability for the users to flip between bar, pie, and line charts without the Publisher having to separately create each one.
1.14 | The solution shall provide the capability for a user to reverse an action when developing displays. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 1.9.1 | This supports an 'Undo' capability.
1.15 | The solution shall provide the capability to analyze data stored in a SQL database. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 2.2
1.16 | The solution shall provide the capability to analyze data stored in an Oracle database. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 2.5
1.17 | The solution shall provide the capability to analyze data stored in MS Excel format. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 3.2
1.18 | The solution shall provide the capability to analyze data stored in CSV format. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 3.3
1.19 | The solution shall provide the capability to display the data under analysis as a formatted report. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 4.5 | Please refer to the Reporting Requirements defined below.
1.2 | The solution shall provide the capability to export charts in PDF format. | Stakeholder | Functional | Data Analysis | Must | Approved |  | Stakeholder Discussions
1.21 | The solution shall provide the capability to display time series data. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 4.7 | A time series is a series of data points indexed (or listed or graphed) in time order.
1.22 | The solution shall provide the capability to execute multi-dimensional analytics. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.1 | Multidimensional analysis (MDA) is a data analysis process that groups data into two categories: data dimensions and measurements. For example, a pivot table in a spreadsheet.
1.23 | The solution shall provide the capability for a user to drill down through data hierarchies. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.8 | Data hierarchy references the practical organization of data, beginning with data fields (a single piece of data) and expanding into larger data sets and groups of data sets, with each subsequently larger data set of a higher rank than the set that came before it.
1.24 | The solution shall provide the capability for predictive analytics/forecasting. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 6.13, 6.14 | Predictive analysis is the act of mining historical data to forecast future events or trends. Predictive analysis hinges upon “predictors”: a variable or set of variables that can be measured to calculate the statistical likelihood of future occurrences.
1.25 | The solution shall provide the capability to analyze trends in the data. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.18
1.26 | The solution shall provide the ability to display trends in the data. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.18
1.27 | The solution shall provide the capability to execute inferential statistical operations. | Stakeholder | Functional | Data Analysis | Could | Approved |  | PMRS 6.19 | Inferential statistics is a set of methods used to draw conclusions or inferences about characteristics of populations based on data from a sample.
1.28 | The solution shall provide the capability to execute descriptive statistical operations. | Stakeholder | Functional | Data Analysis | Could | Approved |  | PMRS 6.20 | Descriptive statistics are used to describe the basic features of the data in a study and provide simple summaries about the sample and the measures.
1.29 | The solution shall provide the capability for a System Administrator to manage the metadata of entities used in an analysis. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 6.22
1.3 | The solution shall provide the capability to aggregate values up a hierarchical dimension. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 2.3.1 | For example, if given monthly data, it can correctly calculate the quarterly and yearly totals.
1.31 | The solution shall provide the capability to support fiscal years. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 2.5.7 | NARA uses fiscal years in numerous reports. These need to be supported without workarounds or programming.
1.32 | The solution shall provide the capability to publish displays with embedded data. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 3.3.1 | To enable displays to run entirely in-memory with no need to re-query the source database.
1.33 | The solution shall provide the capability to re-query the source database when publishing a display. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 3.3.2 | To allow displays to be published so that they re-query their source database on execution, when the data in the display is just too big for memory.
1.34 | The solution shall provide the capability to export data in MS Access format. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 5.2
1.35 | The solution shall provide the capability to export data in MS Excel format. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 5.3
1.36 | The solution shall provide the capability export data in XML format. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 5.4 | Exporting reports in XML allows for end user interactivity of dashboards, higher quality data analytics, etc.
1.37 | The solution shall provide the capability to export data in HTML format. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 5.5 | This is so that it can be displayed on an external website.
1.38 | The solution shall provide the capability to export data in PDF format. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 5.7
2 | National Archives and Records Administration (NARA) users shall be able to create visualizations of data for NARA systems. | Business | N/A | Data Visualization | Must | Approved |  | Stakeholder Discussions
2.1 | The solution shall provide the capability for a user to manage data visualizations. | Stakeholder | Functional | Data Visualization | Must | Approved |  | Stakeholder Discussions | Manage means to create, read, update, delete Data visualizations are generated from data and provides superior tools and techniques to present or analyze data using images in the form of charts, maps, tables, etc., to convey intelligence.
2.2 | The solution shall provide the capability to visualize data as a chart. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 4.2 - 4.4, 4.6
2.2.1 | The solution shall provide the capability for a user to visualize data as a bar chart. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 4.2 | This should include at a minimum - normal, stacked, or stacked 100% bar charts. The different varieties of bar chart are important.
2.2.2 | The solution shall provide the capability for a user to visualize data as a stacked bar chart. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 4.2
2.2.3 | The solution shall provide the capability for a user to visualize data as a 100% stacked bar chart. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 4.2 | A 100% stacked bar chart is an Excel chart type designed to show the relative percentage of multiple data series in stacked bars, where the total (cumulative) of each stacked bar always equals 100%.
2.2.4 | The solution shall provide the capability to visualize data as a pie chart. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 4.3
2.2.5 | The solution shall provide the capability to visualize data as a line chart. | Stakeholder | Functional | Data Analysis | Must | Approved |  | PMRS 4.4
2.2.6 | The solution shall provide the capability to visualize data as a quad chart. | Stakeholder | Functional | Data Analysis | Should | Approved |  | PMRS 4.6 | A quad chart is a specific form of dashboard that has four displays.
2.2.7 | The solution shall provide the capability for a user to visualize data as a bubble chart. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.2.8 | The solution shall provide the capability for a user to visualize data as a radar chart. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.2.9 | The solution shall provide the capability for a user to visualize data as a matrix chart. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.3 | The solution shall provide the capability for a user to visualize data as a heat map. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.4 | The solution shall provide the capability for a user to visualize data as a treemap. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10 | Treemaps display hierarchical data using nested figures, usually rectangles.
2.5 | The solution shall provide the capability for a user to visualize data as a data map. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.6 | The solution shall provide the capability for a user to visualize data as a scatter plot. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.7 | The solution shall provide the capability for a user to visualize data as a network diagram. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.8 | The solution shall provide the capability for a user to visualize data as a tag cloud. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.10
2.9 | The solution shall provide the capability for a user to print a visualization. | Stakeholder | Functional | Data Visualization | Should | Approved |  | PMRS 6.23
2.1 | The solution shall provide a "wizard" functionality to enable a user to develop a visualization. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 1.1 | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a visualization.
2.11 | The solution shall provide an interactive way to visualize multi-dimensional data by direct user manipulation in real-time. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 1.1 | Polaris: A System for Query, Analysis, and Visualization of Multidimensional Databases; Research paper by Chris Stolte, Diane Tang, and Pat Hanrahan; Nov. 2008.
2.11.1 | The solution shall provide the capability to translate drag-and-drop actions into queries. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 1.1
2.11.2 | The solution shall provide the capability to visualize the results of drag-and-drop actions. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 1.1
2.11.3 | The solution shall provide the capability to visualize the data interactively, without the need to pre-define the data table structure. | Stakeholder | Functional | Data Visualization | Must | Approved |  | PMRS 1.1
3 | National Archives and Records Administration (NARA) users shall be able to design and develop dashboards. | Business | N/A | Dashboard | Must | Approved |  | Stakeholder Discussions
3.1 | The solution shall provide the capability for a user to manage a dashboard. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions | Manage means to create, read, update, delete. Dashboards are generated from data, like data visualizations, but are also real-time, regularly updated and function with datasets of many shapes and sizes.
3.2 | The solution shall provide the capability for a user to customize the layout of a dashboard. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions | Allowing the user to control how data is displayed within a dashboard.
3.3 | The solution shall provide the capability for a user to drill down on data displayed within a dashboard. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.4 | The solution shall provide the capability for a user to share a dashboard with one or more users. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.5 | The solution shall provide the capability for a user to export a dashboard. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.5.1 | The solution shall provide the capability for a user to export the contents of a dashboard in MS Excel format. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.5.2 | The solution shall provide the capability for a user to export the contents of a dashboard in MS PowerPoint format. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.5.3 | The solution shall provide the capability for a user to export the contents of a dashboard in PDF format. | Stakeholder | Functional | Dashboard | Should | Approved |  | Stakeholder Discussions
3.6 | The solution shall provide the capability for a user to publish a dashboard. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.7 | The solution shall display the date when the dashboard was last updated. | Stakeholder | Functional | Dashboard | Must | Approved |  | Stakeholder Discussions
3.8 | The solution shall have the ability to create data parameter maps across visualizations and list reports within a dashboard when filters are being utilized. | Stakeholder | Functional | Dashboard | Should | Approved |  | PMRS 1.5 | Quadrants in a dashboard, which contain charts, graphs and list reports, can be easily linked via data parameter maps and data filters, so when one quadrant is changed via a filter, many will update on the fly.
3.9 | The solution shall provide a "wizard" functionality to enable a user to develop a dashboard. | Stakeholder | Functional | Dashboard | Should | Approved |  | PMRS 1.10 | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a dashboard.
3.1 | The solution shall provide the capability to drill down on time hierarchies out-of-the-box. | Stakeholder | Functional | Dashboard | Must | Approved |  | PMRS 1.5 | Time Quadrants in a dashboard for Year/Quarter/Weeks/Month are generated automatically to support multiple database connections and may be displayed in visualizations of charts, graphs and reports.
3.10.1 | The solution shall provide the capability to create hierarchies of the different dimensions, which can be used for drilling up and down in order to see and analyze the data at different levels. | Stakeholder | Functional | Dashboard | Must | Approved |  | PMRS 1.5
3.10.2 | The solution shall provide the capability to filter on date hierarchies interactively through drag-and-drop. | Stakeholder | Functional | Dashboard | Must | Approved |  | PMRS 1.5
3.10.3 | The solution shall provide the capability for the user to select the sort criterion and the sort order for a selected view, based on dynamic filtering. | Stakeholder | Functional | Dashboard | Must | Approved |  | PMRS 1.5
4 | National Archives and Records Administration (NARA) users shall be able to generate standard and ad hoc reports. | Business | N/A | Reporting | Must | Approved |  | Stakeholder Discussions
4.1 | The solution shall provide the capability to generate standard reports. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.2 | The solution shall provide the capability to generate ad hoc reports. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.3 | The solution shall provide the capability for a System Administrator to manage the definition of a report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.3.1 | The solution shall provide the capability for a System Administrator to define the layout of a report definition. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.3.2 | The solution shall provide the capability for a System Administrator to define the data contents of a report definition. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.3.3 | The solution shall provide the capability for a System Administrator to generate a report based on its definition. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.3.4 | The solution shall provide the capability for a user to save a set of parameter values for a report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | Saving parameter values allows reuse. This should only be available where the user can save a version in a personal 'web folder'.
4.3.4.1 | The solution shall provide the capability for a user to run a report using a set of saved parameter values. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | This should only be available where the user can save a version in a personal 'web folder'.
4.4 | The solution shall provide the capability for a user to save an instance of a report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | This should only be available where the user can save a version in a personal 'web folder'.
4.5 | The solution shall provide the capability for a System Administrator to schedule a report to be run by the system. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | Reports could be scheduled for standard and ad hoc reports. A report can be scheduled to run immediately (i.e., on demand) or on a scheduled basis.
4.5.1 | The solution shall provide the capability for a System Administrator to specify the input parameters for a scheduled report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | For example: Date Range = 1/1/17 through 3/30/17
4.5.2 | The solution shall provide the capability for a System Administrator to specify the frequency at which a scheduled report is to be run by the system. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions | For example: annually, quarterly, weekly, daily, etc.
4.5.3 | The solution shall provide the capability for a System Administrator to specify the time of day at which a scheduled report is to be run by the system. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.4 | The solution shall provide the capability for a System Administrator to specify the start date at which a scheduled report is to be run by the system. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.5 | The solution shall provide the capability for a System Administrator to specify the last date at which a scheduled report is to be run by the system. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.6 | The solution shall provide the capability for a System Administrator to cancel a scheduled report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.7 | The solution shall run a report at its scheduled date and time. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.8 | The solution shall record a completion status for an instance of a scheduled report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.9 | The solution shall provide the capability for a System Administrator to edit the schedule for a report. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.10 | The solution shall provide the capability for the owner of a scheduled report to assign users to a report subscription. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.5.11 | The solution shall provide the capability for the owner of a scheduled report to remove users from a report subscription. | Stakeholder | Functional | Reporting | Must | Approved |  | Stakeholder Discussions
4.6 | The solution shall provide the capability for a user to print a report. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 6.25
4.7 | The solution shall provide the capability to distribute reports. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 6.15 | This supports the ability to email reports.
4.7.1 | The solution shall provide the capability to manage distribution lists for emailing a report. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 6.15 | Manage means to create, retrieve, update, and delete email distribution lists.
4.7.2 | The solution shall provide the capability to email reports to multiple email recipients using a distribution list. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 6.15
4.8 | The solution shall provide the capability to export reports in MS Excel format. | Stakeholder | Functional | Reporting | Must | Approved |  | PMRS 5.3
4.9 | The solution shall provide the capability to export reports in XML format. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 5.4 | Exporting reports in XML allows for end user interactivity of dashboards, higher quality data analytics, etc.
4.1 | The solution shall provide the capability to export reports in HTML format. | Stakeholder | Functional | Reporting | Must | Approved |  | PMRS 5.5 | This is so that it can be displayed on an external website.
4.11 | The solution shall provide the ability to export reports in PDF format. | Stakeholder | Functional | Reporting | Should | Approved |  | PMRS 5.7
5 | National Archives and Records Administration (NARA) users shall have access to online training assistance for the system. | Business | N/A | Training | Must | Approved |  | Stakeholder Discussions | This training should be available to any user of the system at no cost.
5.1 | The solution shall provide access to a web tutorial. | Stakeholder | Functional | Training | Should | Approved |  | PMRS 1.7 | The web tutorial shall be accessible either within or external to the solution.
5.2 | The solution shall provide the capability to request online assistance. | Stakeholder | Functional | Training | Must | Approved |  | PMRS 1.8 | Online assistance refers to pop-up assistance provided to the user as they navigate or pan over a label or input field.
5.3 | The solution shall provide online training simulations. | Stakeholder | Functional | Training | Must | Approved |  | Stakeholder Discussions | Training simulations are step-by-step guide videos.
5.4 | The solution shall provide help text via the user interface. | Stakeholder | Functional | Training | Must | Approved |  | Stakeholder Discussions | This may consist of roll-over text or tooltips.
5.5 | The solution shall provide an online knowledge base to allow users to view help topics. | Stakeholder | Functional | Training | Must | Approved |  | Stakeholder Discussions
6 | National Archives and Records Administration (NARA) users shall have an Application Programming Interface (API) for the ingest and integration of external data sources. | Business | N/A | API | Must | Approved |  | PMRS 8.16
7 | The solution shall be accessible to users connected to NARA's internal network. | Stakeholder | Non-Functional | Access | Must | Approved |  | PMRS 6.3
8 | The solution shall provide remote access to users. | Stakeholder | Non-Functional | Access | Should | Approved |  | PMRS 6.4 | The solution shall be accessible through the NARA firewall for staff who work remotely.
9 | The solution shall be 99% available, 24 hours a day, 7 days a week, with the exception of scheduled maintenance downtime. | Stakeholder | Non-functional | Availability | Should | Approved |  | PMRS 11.1
10 | The solution shall provide the capability for backup and recovery of the system. | Stakeholder | Non-Functional | Backup & Recovery | Must | Approved |  | PMRS 10.1
11 | The solution shall be accessible to a user using web browsers. | Stakeholder | Non-functional | Compatibility | Must | Approved |  | PMRS 1.11
11.1 | The solution shall be accessible to a user using Internet Explorer. | Stakeholder | Non-functional | Compatibility | Must | Approved |  | PMRS 1.11 | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
11.2 | The solution shall be accessible to a user using Google Chrome. | Stakeholder | Non-functional | Compatibility | Must | Approved |  | PMRS 1.11 | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
11.3 | The solution shall be accessible to a user using Mozilla Firefox. | Stakeholder | Non-functional | Compatibility | Must | Approved |  | PMRS 1.11 | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
11.4 | The solution shall be accessible to a user using Safari. | Stakeholder | Non-functional | Compatibility | Must | Approved |  | PMRS 1.11 | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
11.5 | The solution shall be compatible with Microsoft Windows 10 Desktop operating system | Stakeholder | Non-functional | Compatibility | Must | Approved |  | Stakeholder Discussions
12 | The solution user interface shall be responsive to mobile devices. | Stakeholder | Non-functional | Compatibility | Should | Approved |  | PMRS 1.12 | This supports dashboards and ad hoc reporting capabilities on mobile devices (e.g., tablets and smartphones).
13 | The solution shall be in compliance with Federal requirements for a FISMA certified solution. | Stakeholder | Non-functional | Compliance | Must | Approved |  | PMRS 7.3 | FISMA: Federal Information Security Management Act
14 | The solution user interface shall comply with Section 508 Standards for Electronic and Information Technology. | Stakeholder | Non-functional | Compliance | Must | Approved |  | PMRS 7.1
15 | The solution shall render dashboards within three to five clicks. | Stakeholder | Non-Functional | Performance | Should | Approved |  | PMRS 1.9 | Includes dashboards rendered on both desktop and mobile devices.
16 | The solution shall render visualizations within three to five clicks. | Stakeholder | Non-Functional | Performance | Should | Approved |  | PMRS 1.9
17 | The solution shall be able to analyze a minimum ten (10) GB of data. | Stakeholder | Non-Functional | Performance | Must | Approved |  | PMRS 6.2 | Note there is currently 5 GB in the PMRS warehouse; this reqt allows for growth.
18 | The solution shall provide the capability to store a minimum of ten (10) GB of data. | Stakeholder | Non-Functional | Performance | Should | Approved |  | PMRS 6.24
19 | The solution shall provide the capability to generate a report within 20 seconds after execution. | Stakeholder | Non-Functional | Performance | Should | Approved |  | PMRS 12.2
20 | The solution shall be in compliance with the NARA Standard IT Security Contractual Requirements. | Stakeholder | Non-functional | Security | Must | Approved |  | PMRS 7.2
21 | The solution shall have open access to an unlimited number of internal NARA users. | Stakeholder | Non-Functional | Security | Must | Approved |  | PMRS 1.2 | Preferably a non-named user server license. This means that the tool must recognize each user as a valid NARA users without the user being required to physically login to the web based tool, allowing for anonymous access. There should be no authentication needed (i.e., no login or password needed) for NARA users to gain access to the system.
22 | The solution shall be able to interface with the PMRS data warehouse. | Business | N/A | System Integration | Must | Approved |  | Stakeholder Discussions
22.1 | The solution shall provide the capability to interface with a data warehouse built on SQL Server 2008 R2. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | PMRS 2.1 | SQL Server 2008 R2 is currently used by PMRS.
22.2 | The solution shall provide the capability to analyze data output from Google Analytics. | Stakeholder | Non-Functional | System Integration | Would | Approved |  | PMRS 8.9
22.3 | The solution shall provide the capability to perform updates using data from a single data source. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | PMRS 13.3
22.4 | The solution shall provide the capability to perform updates to single entities from a single data source. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | PMRS 13.4
22.5 | The solution shall provide built-in connector capability to integrate with structured, unstructured, statistical, and MS Office data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture | Enterprise data
22.5.1 | The solution shall provide built-in connector capability to integrate with XML data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.2 | The solution shall provide built-in connector capability to integrate with Statistical Analysis System (SAS) data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.3 | The solution shall provide built-in connector capability to integrate with Statistical Package for the Social Sciences (SPSS) data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.4 | The solution shall provide built-in connector capability to integrate with R machine learning script data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture | R is a computer language for statistical programming and visualization.
22.5.5 | The solution shall provide built-in connector capability to integrate with Hadoop unstructured data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.6 | The solution shall provide built-in connector capability to integrate with MS Excel spreadsheet data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.7 | The solution shall provide built-in connector capability to integrate with text-based data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
22.5.8 | The solution shall provide Software Development Kit (SDK) connector capability to integrate with Web-based data sources. | Stakeholder | Non-Functional | System Integration | Must | Approved |  | Architecture
23 | The solution shall provide a web-based user interface. | Stakeholder | Non-Functional | User Interface | Must | Approved |  | PMRS 1.1, 1.2, 1.4

## 03-08 PMRS Replacement Reqts (hidden)
| REQUIREMENTS | [14 empty] | DESIGN | DEVELOPMENT | VERIFICATION |  |  |  | DEPLOYMENT PREPARATION |  |  | Source | Location in Evaluation Sheet
Old # | Req # | Requirement Text | Type | Category | Feature | Req Priority | Status | Target Release | Source | Steve Beste's Notes | Original NARA Notes | BA Questions and Comments | Stakeholder Comments and Feedback | Process Description | Use Case | Element | Iteration | Verification Method | Verification Test Case / Step | Verification Status | Verification Criteria | UAT Test Case | UAT Status | Validation Criteria
1 |  | User Interface
1.1 |  | The solution shall provide a web-based, intuitive interface. |  |  | User Interface | Must |  |  | PMRS | [15 empty] | 1 | 1.1.3 and 1.1.5
1.2 |  | The solution shall provide a Web based interface open to unlimited users via anonymous single sign-on authentication. |  |  | Security | Must |  |  | PMRS |  |  | Preferably a non-named user server license
1.3 |  | The solution shall provide the capability for a user to input data for analysis. |  |  | System Analytics | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 6 | 1.11.1
1.4 |  | The solution shall provide an intuitive interface. |  |  |  | Must |  |  | PMRS |  | An intuitive interface shall have features such as drag and drop, and cut and paste. | Move Req down to dashboard | [12 empty] | 7 | 1.9.2 and 2.5.2
1.5 |  | The solution shall synchronize visualizations within a dashboard when filters are being utilized. |  |  | Dashboard | Should |  |  | PMRS |  | Dashboards are generated from data, like data visualizations, but are also real-time, regularly updated and function with datasets of many shapes and sizes. Data visualizations are generated from data and provides superior tools and techniques to present or analyze data using images in the form of charts, maps, tables, etc., to convey intelligence. | [13 empty] | 5 | 1.7.1
1.6 |  | The solution shall provide the ability for a user to select onscreen assistance when navigating the user interface. |  |  | Training | Should |  |  | PMRS |  | Onscreen assistance refers to pop-up assistance provided to the user as they navigate or pan over a label or input field. | [13 empty] | 7 | 1.9.3 and 2.5.3
1.7 |  | The solution shall provide access to a web tutorial [either within or external to the solution] on using the solution. |  |  | Training | Should |  |  | PMRS | Once for the web interface, once for the desktop product's interface. | [14 empty] | 7 | 1.9.5 and 2.5.5
1.8 |  | The solution shall provide the ability to request online assistance within the tool. |  |  | Training | Must |  |  | PMRS | Once for the web interface, once for the desktop product's interface. | [14 empty] | 7 | 1.9.4 and 2.5.4
1.9 |  | The solution shall render dashboards or other types of user created visualizations within three to five clicks. |  |  | Performance | Should |  |  | PMRS | [15 empty] | 7 | 1.9.8
1.10 |  | The solution shall provide "wizard" functionality for building dashboards. |  |  | Dashboard | Should |  |  | PMRS |  | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a dashboard. | [13 empty] | 7 | 2.5.6
|  | The solution shall provide "wizard" functionality for user-created visualizations. |  |  | Data Visualization | [5 empty] | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a visualization.
1.11 |  | The solution shall be accessible via NARA-supported browsers. |  |  |  | Must |  |  | PMRS |  | The solution shall support at least 2 of the following three browsers: Firefox ESR - 31.3.0 ESR, Google Chrome Version 37.0.2062.124 m, or Internet Explorer Version 8.0.7601.17514. If only 2 browsers are to be supported the preferred 2 are Firefox and Chrome. | [13 empty] | 7 | 1.1.3
|  | The solution shall be accessible to an user using web browsers. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS
|  | The solution shall be accessible to an user using web browsers. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS |  |  | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
|  | The solution shall be accessible to an user using Internet Explorer. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS |  |  | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
|  | The solution shall be accessible to an user using Google Chrome. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS |  |  | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
|  | The solution shall be accessible to an user using Mozilla Firefox. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS |  |  | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
|  | The solution shall be accessible to an user using Safari. | Stakeholder | Non-functional | Compatibility | Must |  |  | PMRS
1.12 |  | The solution shall provide a mobile interface. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | This entails providing dashboards and ad hoc reporting capabilities on mobile devices (e.g., tablets and smartphones). | [13 empty] | 7 | 1.1.4
|  | The solution user interface shall be responsive to mobile devices. | Stakeholder | Non-functional | Compatibility |  |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | This entails providing dashboards and ad hoc reporting capabilities on mobile devices (e.g., tablets and smartphones). | Add notes to high level rpt req n dashb to support mobile devices
2 |  | Sources of Input |  |  |  | #N/A
2.1 |  | The solution shall provide the capability to interface with a data warehouse built on SQL Server 2008 R2. | Stakeholder | Functional | System Integration | Must |  |  | PMRS |  | SQL Server 2008 R2 is currently used by PMRS. | [13 empty] | 1 | 2.1.6
2.2 |  | The solution shall provide the capability to analyze data stored in SQL databases. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 6 | 2.1.6
2.5 |  | The solution shall provide the capability to analyze data stored in an Oracle database. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 2.1.5
[25 empty] | 4 | --
3 |  | File Formats of Input |  |  |  | #N/A
3.2 |  | The solution shall provide the capability to analyze data stored in Excel spreadsheets. |  |  | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 2.1.3
3.3 |  | The solution shall provide the capability to analyze data stored in character-separated values (csv) files. |  |  | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 2.1.2
4 |  | Types of Output |  |  |  | #N/A
4.1 |  | The solution shall provide the capability for a user to create interactive dashboards. |  |  |  | Must |  |  | PMRS | The ideal here is self-service dashboards (1.8). The fallback is that publishers must create them (3.5.1). | [14 empty] | 1 | 1.8.1, 1.8.2 and 3.5.1
|  | The solution shall provide the capability for a user to manage a dashboard. | Stakeholder | Functional | Dashboards | [5 empty] | Manage means to create, read, update, delete
|  | The solution shall display the date when the dashboard was last updated. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to customize the layout of a dashboard. | Stakeholder | Functional | Dashboards | [5 empty] | Allowing the user to control how data is displayed within a dashboard.
|  | The solution shall provide the capability for a user to drill-down on data displayed within a dashboard. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to share a dashboard with another user. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to share a dashboard with users within a group. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to export a dashboard. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to export the contents of a dashboard in MS Excel format. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to export the contents of a dashboard in MS PowerPoint format. | Stakeholder | Functional | Dashboards
|  | The solution shall provide the capability for a user to publish a dashboard within the solution. | Stakeholder | Functional | Dashboards
4.2 |  | The solution shall provide the capability for a user to visualize data as a bar chart. | Stakeholder | Functional | Data Visualization | Must |  |  | PMRS | The different varieties of bar chart are important. | This should include at a minimum - normal, stacked, or stacked 100% bar charts. | [13 empty] | 4 | 1.5.2, 1.5.3 and 1.5.4
|  | The solution shall provide the capability for a user to visualize data as a normal bar chart. | Stakeholder | Functional | Data Visualization
|  | The solution shall provide the capability for a user to visualize data as a stacked bar chart. | Stakeholder | Functional | Data Visualization
|  | The solution shall provide the capability for a user to visualize data as a 100% stacked bar chart. | Stakeholder | Functional | Data Visualization
4.3 |  | The solution shall provide the capability to display the data under analysis as a pie chart. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 1.5.6
4.4 |  | The solution shall provide the capability to display the data under analysis as a line chart. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 1.5.5
|  | The solution shall provide the capability to export the data displayed in charts in .pdf format. | Stakeholder | Functional | System Analytics | [6 empty] | Que: Is this format applicable? Please free to add or remove formats
|  | The solution shall provide the capability to export the data displayed in charts in MS Word format. | Stakeholder | Functional | System Analytics | [6 empty] | Que: Is this format applicable? Please free to add or remove formats
|  | The solution shall provide the capability to export the data displayed in charts in MS Excel format. | Stakeholder | Functional | System Analytics | [6 empty] | Que: Is this format applicable? Please free to add or remove formats
4.5 |  | The solution shall provide the capability to display the data under analysis as a formatted report. | Stakeholder | Functional | Reporting | Must |  |  | PMRS | [15 empty] | 4 | 1.5.1
4.6 |  | The solution shall provide the capability to display the data under analysis as a quad chart. | Stakeholder | Functional | System Analytics | Should |  |  | PMRS | A quad chart is just a specific form of dashboard that has four displays. Hence, covered by the dashboard requirement. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4 | 1.8.1
4.7 |  | The solution shall provide the capability to display time series data. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 6 | 1.2.5
2.6 |  | The solution shall provide the capability to analyze its own transaction log. |  |  |  | Should |  |  | PMRS | N/A. These tools don't keep transaction logs. |  | Que: What are transaction logs? Is this capability supported by this type of tool per Steve' comments?
4.9 |  | The solution shall have the ability to generate and display a transaction log. |  |  |  | Should |  |  | PMRS | N/A. Conceptually, these are not the kind of product that keeps a transaction log - any more than Excel does. |  | See comments above. | [12 empty] | 4 | -
5 |  | File Formats of Output |  |  |  | #N/A
5.1 |  | The solution shall provide the capability to export data to MS Word. | Stakeholder | Functional | Reporting | Should |  |  | PMRS | Dropped. If "data" means the formatted display, then a screen shot taken with the Windows Snipping Tool does the job whether the tool provides a screen-capture feature or not. Hence, a superfluous feature. If "data" means the underlying data, nobody wants an unformatted text blob. You'd send it to Excel. | [14 empty] | 4 | -
5.2 |  | The solution shall provide the capability to export data to MS Access. | Stakeholder | Functional | Reporting | Should |  |  | PMRS | [15 empty] | 4 | 1.12.3 and 2.2.3
5.3 |  | The solution shall provide the capability to export data to export data to MS Excel. | Stakeholder | Functional | Reporting | Must |  |  | PMRS | [15 empty] | 3 | 1.12.4 and 2.2.4
5.4 |  | The solution shall provide the capability to export data to export data in a XML format. | Stakeholder | Functional | Reporting | Should |  |  | PMRS | Exporting reports in XML allows for end user interactivity of dashboards, higher quality data analytics, etc. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4 | 1.12.6 and 2.2.6
5.5 |  | The solution shall provide the capability to export data to export data in a HTML format. | Stakeholder | Functional | Reporting | Must |  |  | PMRS |  | This is so that it can be displayed on an external website. | [13 empty] | 5 | 1.12.7 and 2.2.7
5.7 |  | The solution shall provide the ability to export data in a PDF format. | Stakeholder | Functional | Reporting | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
6 |  | Other Functional and Technical Requirements |  |  |  | #N/A
6.1 |  | The solution shall provide the capability to execute multi-dimensional analytics. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 1 | 1.2.1 - 1.2.4
6.2 |  | The solution shall be able to analyze at a minimum 10 GB of data. | Stakeholder | Functional | Performance | Must |  |  | PMRS |  | (currently 5 GB in PMRS warehouse.) | [13 empty] | 5 | 1.10.3
6.3 |  | The solution shall be accessible to users connected to NARA's internal network. | Stakeholder | Non-Functional | Access | Must |  |  | PMRS | [15 empty] | 1 | 1.1.1
|  | The solution shall be capable of using NARA’s identity management and authentication service for access control. | Stakeholder | Non-Functional | Security | [5 empty] | LDAP Authentication and Security Assertion Markup Language (SAML)
6.4 |  | The solution shall provide remote access to authorized users. | Stakeholder | Non-Functional | Access | Should |  |  | PMRS |  | The solution shall be accessible through the NARA firewall for staff who work remotely. | [13 empty] | 7 | 1.1.2
6.5 |  | The solution shall allow self-service use of data cubes. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | Dropped as a separate item. All the Consumer features add up to this. And both tools do it. | [14 empty] | 1 | -
6.8 |  | The solution shall provide the capability for a user to drill down through data hierarchies. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 1 | 1.2.4
6.9 |  | The solution shall provide the capability for a user to access canned reports. | Stakeholder | Functional | Reporting | Must |  |  | PMRS | [15 empty] | 1 | 3.2.1
|  | The solution shall provide the capability for an authorized user to manage the definition of a report. | Stakeholder | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to define the layout of a report definition. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to define the data contents of a report definition. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to schedule a report to be run by the system. | Stakeholder | Functional | Reporting | [5 empty] | Reports could be scheduled for standard and adhoc reports. A report can be scheduled to run immediately (i.e., on demand) or on a scheduled basis.
|  | The solution shall provide the capability for an authorized user to specify the input parameters for a scheduled report. | System | Functional | Reporting | [5 empty] | For example: Date Range = 1/1/17 through 3/30/17
6.16 |  | The solution shall provide the capability for an authorized user to specify the frequency at which a scheduled report is to be run by the system. | System | Functional | Reporting | [5 empty] | For example: annually, quarterly, weekly, daily, etc
|  | The solution shall provide the capability for an authorized user to specify the time of day at which a scheduled report is to be run by the system. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to specify the start date at which a scheduled report is to be run by the system. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to specify the last date at which a scheduled report is to be run by the system. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to cancel a scheduled report. | System | Functional | Reporting
|  | The solution shall run a report at its scheduled date and time. | System | Functional | Reporting
|  | The solution shall record a completion status for an instance of a scheduled report. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to edit the schedule for a report. | System | Functional | Reporting
|  | The solution shall provide the capability for the owner of a scheduled report to assign and remove users from a report subscription. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to generate a report based on its definition. | Stakeholder | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to save a set of parameter values for a report. | System | Functional | Reporting | [5 empty] | Saving parameter values allows reuse.
|  | The solution shall provide the capability for an authorized user to run a report using a set of saved parameter values. | System | Functional | Reporting
|  | The solution shall provide the capability for an authorized user to save an instance of a report. | System | Functional | Reporting
6.25 |  | The solution shall provide the capability for a user to print a report. | Stakeholder | Functional | Reporting | Should |  |  | PMRS | [15 empty] | 5 | 1.12.1 and 2.2.1
6.1 |  | The solution shall allow users to visualize data in multiple ways. |  |  |  | Should |  |  | PMRS |  | heat map, treemap, scatter plot, matrix chart, network diagram, bubble chart, tag cloud, radar chart, data map, see also http://www.visual-literacy.org/periodic_table/periodic_table.html
6.10 |  | The solution shall provide the capability for a user to visualize data as a heat map. | System | Functional | Data Visualization | Should |  |  | PMRS | [15 empty] | 1 | 1.5.8
|  | The solution shall provide the capability for a user to visualize data as a treemap. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a scatter plot. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a matrix chart. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a network diagram. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a bubble chart. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a tag cloud. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a radar chart. | System | Functional | Data Visualization | Should |  |  | PMRS
|  | The solution shall provide the capability for a user to visualize data as a data map. | System | Functional | Data Visualization | Should |  |  | PMRS
6.11 |  | The solution shall provide the capability for a user to perform ad hoc calculations. | System | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 1 | 1.4.3
6.12 |  | The solution shall provide the capability for a user to filter data on multiple variables, data elements, or attributes. |  |  |  | Must |  |  | PMRS
6.12 |  | The solution shall provide the capability for a user to filter data on multiple variables. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 1.3.1
6.12 |  | The solution shall provide the capability for a user to filter data on multiple data elements. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.12 |  | The solution shall provide the capability for a user to filter data on multiple attributes. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.13 |  | The solution shall provide the capability for predictive analytics. | Stakeholder | Functional | System Analytics | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4 | 2.4.1
6.14 |  | The solution shall provide the capability for forecasting. | Stakeholder | Functional | System Analytics | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4 | 2.4.4
6.15 |  | The solution shall provide the ability to automatically email reports to email addresses. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4 | 3.2.2
6.15 |  | The solution shall provide the capability to distribute reports. | Stakeholder | Functional | Reporting | Should |  |  | PMRS
|  | The solution shall provide the capability to manage distribution lists for emailing a report. | Stakeholder | Functional | Reporting | Should |  |  | PMRS |  | Manage means to create, retrieve, update, and delete email distribution lists.
|  | The solution shall provide the capability to email reports to multiple email recipients using a distribution list. | Stakeholder | Functional | Reporting | Should |  |  | PMRS
6.18 |  | The solution shall provide the capability to analyze trends in the data. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 1.2.5
6.18 |  | The solution shall provide the ability to display trends in the data. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 4 | 1.2.5
6.19 |  | The solution shall provide the capability to execute inferential statistical operations. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 5 | 2.4.2
6.20 |  | The solution shall provide the capability to execute descriptive statistical operations. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 5 | 2.4.3
6.21 |  | The solution shall allow the user to specify whether the summary displays the most recent value (stock variable) or the sum of the data for a given period (flow variable) when summarizing numeric data. |  |  |  | Must |  |  | PMRS | [15 empty] | 5 | 2.3.2
6.21 |  | When summarizing numeric data, the solution shall provide the capability to display the summary of the most recent value (stock variable). | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.21 |  | The solution shall provide the capability for a user to record that the summary of numeric data is a Stock Variable. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.21 |  | When summarizing numeric data, the solution shall provide the capability to display the sum of the data for a given period (flow variable). | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.21 |  | The solution shall provide the capability for a user to record that the summary of numeric data is a Flow Variable. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS
6.22 |  | The solution shall provide the ability to manage metadata to describe all entities used in an analysis. | Stakeholder | Functional | System Analytics | Must |  |  | PMRS | [15 empty] | 5 | 1.9.6
6.23 |  | The solution shall provide the capability for a user to print a visualization. | Stakeholder | Functional | Data Visualization | Should |  |  | PMRS |  | Manage means to create, retrieve, update, and delete. | [13 empty] | 5 | 1.12.1 and 2.2.1
6.24 |  | The solution shall provide the capability to store a minimum of ten (10) gigabytes of data. |  |  | Performance | Should |  |  | PMRS | N/A. Neither of these tools is a data warehouse. They don't store data. Instead, I substituted a test of whether the tool can display the largest PMRS cube in memory. That has 3.56 million data points. |  | We need to confirm with the stakeholders and System Engineering to find out if storage is only needed for a minimum of 10 gigabytes of data. | [12 empty] | 7 | 1.10.2
7 |  | Compliance
7.1 |  | The solution user interface shall be Section 508 compliant. | Stakeholder | Non-functional | Usability | Must |  |  | PMRS
11.1 |  | The solution shall be available 99% of 24 hours by 7 days a week excluding scheduled downtime. | Stakeholder | Non-functional | Availability | Should |  |  | PMRS | N/A. Applies mainly to SaaS. For software at NARA, this is a function of NARANET and server uptime, which is not a product attribute.
7.2 |  | The solution shall be in compliance with the NARA Standard IT Security Contractual Requirements. | Stakeholder | Non-functional | Security & Authentication | Must |  |  | PMRS
7.3 |  | The solution shall be in compliance with Federal requirements for a FISMA certified solution. | Stakeholder | Non-functional | Compliance | Must |  |  | PMRS | [15 empty] | 5 | 4.2.1
8 |  | External Interface
8.7 |  | The solution shall provide the capability to analyze data output from PMRS. | Stakeholder | Functional | System Integration | Must |  |  | PMRS | Runs on SQL Server. | [14 empty] | 4 | 2.1.6
8.8 |  | The solution shall provide the capability to analyze data output from Web Trends Analytics. |  |  | System Integration | Should |  |  | N/A | N/A. Web Trends no longer used. |  | Per Steve's comment, is this reqt still applicable? | [12 empty] | 4 | -
8.9 |  | The solution shall provide the capability to analyze data output from Google Analytics. |  |  | System Integration | Would |  |  | PMRS | Google analytics is gaining traction is is being used throughout NARA. There may be a requirement in the future for PMRS to connect to Google Analytics. Is not a current function of Databeacon but the procured BI tool would be 'nice to have' this functionality. | [14 empty] | 4 | 2.1.9
8.16 |  | The solution shall provide an Application Programming Interface (API) for the ingest and integration of external data sources. | Stakeholder | Non-functional | API | Must |  |  | PMRS | API support for connectivity to cloud based solutions is critical for a modern BI tool. Is not a current function of Databeacon but the procured BI tool 'must have' this functionality. A feature PMRS is looking for.
9 |  | Support & Maintenance
9.1 |  | The solution provider shall install, configure, patch, provide timely upgrades as required, and support as specified in the Service Level Agreements of the contract. |  |  |  | Must |  |  | PMRS | N/A. Applies only to Software as a Service (SaaS), which is not the case with these particular tools. |  | This is a contractual reqt and should be removed | [12 empty] | 7 | -
10 |  | Backup & Recovery
10.1 |  | The solution shall provide the capability for backup and recovery of the system. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | Collapsed into one item so as not to give undue weight to backup and recovery. | [14 empty] | 7 | 4.1.1
10.2 |  | The solution shall provide the capability for the backup of application files. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.3 |  | The solution shall provide the capability for the backup of database files. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.4 |  | The solution shall provide the capability to schedule nightly incremental backups. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.5 |  | The solution shall provide the capability to schedule weekly full backups. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.6 |  | The solution shall provide the capability to manually perform a backup. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.7 |  | The solution shall provide the capability to cancel a scheduled backup process. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.8 |  | The solution shall provide the capability to cancel a manual backup process. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.9 |  | The solution shall provide the capability to recover application files to restore operational capability. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.10 |  | The solution shall provide the capability to recover database files to restore operational capability. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.11 |  | The solution shall provide the capability to recover from a hardware failure. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
10.12 |  | The solution shall provide the capability to recover from a physical site outage. | Stakeholder | Non-Functional | Backup & Recovery | Must |  |  | PMRS | [15 empty] | 7 | 4.1.1
12 |  | Performance | [22 empty] | 7
12.2 |  | The solution shall provide the capability to generate a report within 20 seconds after execution. | Stakeholder | Non-Functional | Performance | Should |  |  | PMRS | [15 empty] | 7 | 1.10.1
13 |  | Information Management
13.1 |  | The solution shall accept user-specified, periodic updates from data sources. | Stakeholder | Functional | System Integration | Must |  |  | PMRS | I collapsed all these system-specific details on the grounds that once the tools can connect to sources (evaluated in Section 8), its update features apply equally to all. | [14 empty] | 1 | 2.1
13.1.6 |  | The solution shall accept user-specified, periodic data updates from the PMRS system. | Stakeholder | Functional | System Integration | Should |  |  | PMRS | [15 empty] | 7 | 2.1
13.1.8 |  | The solution shall accept user-specified, periodic data updates from the Web Trends Analytics system. |  |  | System Integration | Should |  |  | N/A | Web Trends not being used. N/A | [14 empty] | 7 | 2.1
13.3 |  | The solution shall provide the capability to perform updates using data from a single data source. | Stakeholder | Functional | System Integration | Must |  |  | PMRS | [15 empty] | 5 | 3.4.1
13.4 |  | The solution shall provide the ability to perform updates to single entities from a single data source. | Stakeholder | Functional | System Integration | Must |  |  | PMRS | [15 empty] | 5 | 3.4.1
14 |  | Training Requirement | [6 empty] | PMRS
14.1 |  | The solution shall provide online help. | Stakeholder | Functional | Training | [5 empty] | This training will be available to any user of the system at no cost.
1.4.1 |  | The solution shall provide the capability for a user to display certain measures and hide others. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | Many PMRS cubes show lots of measures - # of, % of, holdings in cu.ft., holdings in pages, start-of-year holdings, and so on. The consumer often wants to hide the measures that don't interest him at the moment, the better to de-clutter the view.
1.4.2 |  | The solution shall provide the capability for a user to display two or more measures simultaneously. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | Sometimes uses want to compare measures in a display, such as a seeing the number of respondents to a survey, the number of happy respondents, and the % happy. The tool should support this.
1.4.4 |  | The solution shall provide the capability for a user to see the values of data points on graphical displays. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | This is a minor feature. When looking at a graphical display, it lets users inspect the data values underneath an object by mousing over it. | The user should be able to see the values by mousing over the data point.
1.6.1 |  | The solution shall provide the capability for a user to swap between text and graphical displays of the same data. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | With Databeacon, the user can start with a table, click a button, and see a bar chart, all self-serve. By contrast, with Tableau, if you start with a text display, no charts are available unless the Publisher has created them. This design greatly increases the parts count for the Publisher.
1.6.2 |  | The solution shall provide the capability for a user to swap between types of graphical displays. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | Likewise, we want users to be able to flip between bar, pie, and line charts without the Publisher having to have separately created each one.
1.9.1 |  | Undo – The consumer displays have a step-wise undo feature (usually an undo button). | Stakeholder | Functional | System Analytics |  |  |  | PMRS | This is an obvious requirement.
1.9.1 |  | The solution shall provide the capability for a user to reverse an action when developing displays. | Stakeholder | Functional | System Analytics |  |  |  | PMRS |  | This supports an 'Undo' capability.
1.12.2 |  | The consumer can export a display as a PDF file. |  |  | See comment |  |  |  | PMRS | I'm sure there will be a demand for PDFs.
2.5.1 |  | Undo – The analyst displays have a step-wise undo feature (usually an undo button). |  |  | See comment |  |  |  | PMRS
2.2.2 |  | The analyst can export a display as a PDF file. |  |  | See comment |  |  |  | PMRS |  |  | Duplicate Reqt
2.3.1 |  | The solution shall provide the capability to aggregate values up a hierarchical dimension. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | It's not enough to drill in and out. We want the tool to calculate sums correctly when we do. | For example, if given monthly data, it can calculate the quarterly and yearly totals.
2.5.7 |  | The solution shall provide the capabiilty to support fiscal years. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | NARA uses fiscal years in hundreds of reports. These need to be supported without workarounds or programming.
3.3.1 |  | The solution shall provide the capabiilty to publish displays with embedded data. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | We want an in-memory product because they run faster and our (PMRS) data is small. | To enable displays to run entirely in memory with no need to re-query the source database.
3.3.2 |  | The solution shall provide the capability to re-query the source database when publishing a display. | Stakeholder | Functional | System Analytics |  |  |  | PMRS | But we want this, too, for when the data in the display is just too big for memory. | To allow displays to be published so that they do re-query their source database on execution, when the data in the display is just too big for memory.
3.5.4 |  | Anonymous users – The tool supports use by anonymous users. (Thus, the administrator does not need to maintain a list of all users, just those with non-default dashboards.) | [6 empty] | PMRS | Conversely, we don't want the Publishers to have to maintain user lists when most users don't need special treatment, and hence can be anonymous. |  | Que: Does this mean that the tool should not require a user to have a username or password?
4.3.1 |  | During the evaluation, the vendor’s support was readily available and competent. |  |  | Contractual Requirement. |  |  |  | PMRS | This is a proxy for the kind of customer support we can expect in the future. |  | This is a contractual reqt and should be removed
4.3.2 |  | The product has an online community forum ready to answer questions. |  |  | Contractual Requirement. |  |  |  | PMRS | This kind of support enormously eases implementation and ongoing work. |  | This is a contractual reqt and should be removed

## Copy of Requirements 0407 (hidden)
| REQUIREMENTS | [14 empty] | DESIGN | DEVELOPMENT | VERIFICATION |  |  |  | DEPLOYMENT PREPARATION |  |  | REQ Tag | Requirement text | PMRS or Enterprise | Source |  | Priority | Location in Evaluation Sheet | Steve Beste's Notes | NARA Reviewer Notes Regarding Steve's Changes | Original NARA Notes
| Req # | Requirement Text | Type | Category | Feature | Req Priority | Status | Target Release | Source | Steve Beste's Notes | Original NARA Notes | BA Questions and Comments | Stakeholder Comments and Feedback | Process Description | Use Case | Element | Iteration | Verification Method | Verification Test Case / Step | Verification Status | Verification Criteria | UAT Test Case | UAT Status | Validation Criteria
1 |  | User Interface |  |  |  | Must | [18 empty] | 1 | User Interface
2 | 0 | The solution shall provide a web-based interface. |  |  |  | Must |  |  | PMRS | [15 empty] | 1.1 | The solution shall provide a web-based interface. | PMRS | 1 | #ERROR! | H | 1.1.3 and 1.1.5
3 |  | Web based interface open to unlimited users via anonymous single sign-on authentication, preferably a non-named user server license |  |  |  | Must |  |  | PMRS | [15 empty] | 1.2 | Web based interface open to unlimited users via anonymous single sign-on authentication, preferably a non-named user server license | PMRS |  | #ERROR! | H
4 |  | The solution shall provide the ability for the user to directly input data for analysis. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 1.3 | The solution shall provide the ability for the user to directly input data for analysis. | PMRS | 6 | #ERROR! | M | 1.11.1 | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
5 |  | The solution shall provide an intuitive interface. |  |  |  | Must |  |  | PMRS |  | An intuitive interface shall have features such as drag and drop, and cut and paste. | [13 empty] | 1.4 | The solution shall provide an intuitive interface. | PMRS | 7 | #ERROR! | H | 1.9.2 and 2.5.2 |  |  | An intuitive interface shall have features such as drag and drop, and cut and paste.
6 |  | The solution shall synchronize visualizations within a dashboard when filters are being utilized. |  |  |  | Should |  |  | PMRS | [15 empty] | 1.5 | The solution shall synchronize visualizations within a dashboard when filters are being utilized. | PMRS | 5 | #ERROR! | M | 1.7.1
7 |  | The solution shall provide the ability for a user to select onscreen assistance when navigating the user interface. |  |  |  | Should |  |  | PMRS |  | Onscreen assistance refers to pop-up assistance provided to the user as they navigate or pan over a label or input field. | [13 empty] | 1.6 | The solution shall provide the ability for a user to select onscreen assistance when navigating the user interface. | PMRS | 7 | #ERROR! | M | 1.9.3 and 2.5.3 |  |  | Onscreen assistance refers to pop-up assistance provided to the user as they navigate or pan over a label or input field.
8 |  | The solution shall provide access to a web tutorial [either within or external to the solution] on using the solution. |  |  |  | Should |  |  | PMRS | Once for the web interface, once for the desktop product's interface. | [14 empty] | 1.7 | The solution shall provide access to a web tutorial [either within or external to the solution] on using the solution. | PMRS | 7 | #ERROR! | M | 1.9.5 and 2.5.5 | Once for the web interface, once for the desktop product's interface.
9 |  | The solution shall provide the ability to request online assistance within the tool. |  |  |  | Must |  |  | PMRS | Once for the web interface, once for the desktop product's interface. | [14 empty] | 1.8 | The solution shall provide the ability to request online assistance within the tool. | PMRS | 7 | #ERROR! | H | 1.9.4 and 2.5.4 | Once for the web interface, once for the desktop product's interface.
10 |  | The solution shall render dashboards or other types of user created visualizations within three to five clicks. |  |  |  | Should |  |  | PMRS | [15 empty] | 1.9 | The solution shall render dashboards or other types of user created visualizations within three to five clicks. | PMRS | 7 | #ERROR! | M | 1.9.8
11 |  | The solution shall provide "wizard" functionality for building dashboards and user created visualizations. |  |  |  | Should |  |  | PMRS |  | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a dashboard or visualization. | [13 empty] | 1.10 | The solution shall provide "wizard" functionality for building dashboards and user created visualizations. | PMRS | 7 | #ERROR! | M | 2.5.6 |  |  | A software wizard or setup assistant that presents the user with a sequence of dialog boxes that lead the user through a series of well-defined steps to create a dashboard or visualization.
12 |  | The solution shall be accessible via NARA-supported browsers. |  |  |  | Must |  |  | PMRS |  | The solution shall support at least 2 of the following three browsers: Firefox ESR - 31.3.0 ESR, Google Chrome Version 37.0.2062.124 m, or Internet Explorer Version 8.0.7601.17514. If only 2 browsers are to be supported the preferred 2 are Firefox and Chrome. | [13 empty] | 1.11 | The solution shall be accessible via NARA-supported browsers. | PMRS | 7 | #ERROR! | H | 1.1.3 |  |  | The solution shall support at least 2 of the following three browsers: Firefox ESR - 31.3.0 ESR, Google Chrome Version 37.0.2062.124 m, or Internet Explorer Version 8.0.7601.17514. If only 2 browsers are to be supported the preferred 2 are Firefox and Chrome.
13 |  | The solution shall provide a mobile interface. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | This entails providing dashboards and ad hoc reporting capabilities on mobile devices (e.g., tablets and smartphones). | [13 empty] | 1.12 | The solution shall provide a mobile interface. | PMRS | 7 | #ERROR! | M | 1.1.4 | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. |  | This entails providing dashboards and ad hoc reporting capabilities on mobile devices (e.g., tablets and smartphones).
14 |  | Sources of Input |  |  |  | #N/A | [18 empty] | 2 | Sources of Input |  |  | #ERROR!
15 |  | The solution shall be able to interface with a data warehouse built on SQL Server 2008 R2. |  |  |  | Must |  |  | PMRS |  | SQL Server 2008 R2 is currently used by PMRS. | [13 empty] | 2.1 | The solution shall be able to interface with a data warehouse built on SQL Server 2008 R2. | PMRS | 1 | #ERROR! | H | 2.1.6 |  |  | SQL Server 2008 R2 is currently used by PMRS.
16 |  | The solution shall provide the ability to analyze data stored in SQL databases. |  |  |  | Must |  |  | PMRS | [15 empty] | 2.2 | The solution shall provide the ability to analyze data stored in SQL databases. | PMRS | 6 | #ERROR! | H | 2.1.6
200 |  | The solution shall provide the ability to analyze data stored in disparate databases joined for analysis purposes. |  |  |  | Must |  |  | Enterprise | [15 empty] | 2.3 | The solution shall provide the ability to analyze data stored in disparate databases joined for analysis purposes. | Enterprise | 6 | #ERROR! | H | 2.1.1
201 |  | The solution shall be able to pull and combine data from disparate databases for a common analysis. |  |  |  | Must |  |  | Enterprise | [15 empty] | 2.4 | The solution shall be able to pull and combine data from disparate databases for a common analysis. | Enterprise | 6 | #ERROR! | H | 2.1.1
19 |  | The solution shall provide the ability to analyze data stored in an Oracle database. |  |  |  | Must |  |  | PMRS | [15 empty] | 2.5 | The solution shall provide the ability to analyze data stored in an Oracle database. | PMRS | 4 | #ERROR! | H | 2.1.5
20 |  | The solution shall have the ability to analyze its own transaction log. |  |  |  | Should |  |  | PMRS | N/A. These tools don't keep transaction logs. | [14 empty] | 2.6 | The solution shall have the ability to analyze its own transaction log. | PMRS | 4 | #ERROR! | M | -- | N/A. These tools don't keep transaction logs.
21 |  | File Formats of Input |  |  |  | #N/A | [18 empty] | 3 | File Formats of Input |  |  | #ERROR!
202 |  | The solution shall provide the ability to analyze data stored in individual XML documents and sets of XML documents. |  |  |  | Would |  |  | Enterprise | [15 empty] | 3.1 | The solution shall provide the ability to analyze data stored in individual XML documents and sets of XML documents. | Enterprise | 3 | #ERROR! | L | 2.1.12
203 |  | The solution shall provide the ability to analyze data stored in Excel spreadsheets. |  |  |  | Must |  |  | Enterprise | [15 empty] | 3.2 | The solution shall provide the ability to analyze data stored in Excel spreadsheets. | Enterprise | 4 | #ERROR! | H | 2.1.3
204 |  | The solution shall provide the ability to analyze data stored in character-separated values (csv) files. |  |  |  | Must |  |  | Enterprise | [15 empty] | 3.3 | The solution shall provide the ability to analyze data stored in character-separated values (csv) files. | Enterprise | 4 | #ERROR! | H | 2.1.2
25 |  | Types of Output |  |  |  | #N/A | [18 empty] | 4 | Types of Output |  |  | #ERROR!
26 |  | The solution shall allow users to create interactive dashboards. |  |  |  | Must |  |  | PMRS | The ideal here is self-service dashboards (1.8). The fallback is that publishers must create them (3.5.1). | [14 empty] | 4.1 | The solution shall allow users to create interactive dashboards. | PMRS | 1 | #ERROR! | H | 1.8.1, 1.8.2 and 3.5.1 | The ideal here is self-service dashboards (1.8). The fallback is that publishers must create them (3.5.1).
27 |  | The solution shall provide the ability to display the data under analysis as a bar chart. |  |  |  | Must |  |  | PMRS | The different varieties of bar chart are important. | This should include at a minimum - normal, stacked, or stacked 100% bar charts. | [13 empty] | 4.2 | The solution shall provide the ability to display the data under analysis as a bar chart. | PMRS | 4 | #ERROR! | H | 1.5.2, 1.5.3 and 1.5.4 | The different varieties of bar chart are important. |  | This should include at a minimum - normal, stacked, or stacked 100% bar charts.
28 |  | The solution shall provide the ability to display the data under analysis as a pie chart. |  |  |  | Must |  |  | PMRS | [15 empty] | 4.3 | The solution shall provide the ability to display the data under analysis as a pie chart. | PMRS | 4 | #ERROR! | H | 1.5.6
29 |  | The solution shall provide the ability to display the data under analysis as a line chart. |  |  |  | Must |  |  | PMRS | [15 empty] | 4.4 | The solution shall provide the ability to display the data under analysis as a line chart. | PMRS | 4 | #ERROR! | H | 1.5.5
30 |  | The solution shall provide the ability to display the data under analysis as a formatted report. |  |  |  | Must |  |  | PMRS | [15 empty] | 4.5 | The solution shall provide the ability to display the data under analysis as a formatted report. | PMRS | 4 | #ERROR! | H | 1.5.1
31 |  | The solution shall provide the ability to display the data under analysis as a quad chart. |  |  |  | Should |  |  | PMRS | A quad chart is just a specific form of dashboard that has four displays. Hence, covered by the dashboard requirement. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 4.6 | The solution shall provide the ability to display the data under analysis as a quad chart. | PMRS | 4 | #ERROR! | M | 1.8.1 | A quad chart is just a specific form of dashboard that has four displays. Hence, covered by the dashboard requirement. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
32 |  | The solution shall provide the ability to display time series data. |  |  |  | Must |  |  | PMRS | [15 empty] | 4.7 | The solution shall provide the ability to display time series data. | PMRS | 6 | #ERROR! | H | 1.2.5
205 |  | The solution shall provide the ability to display the data under analysis as a space map. |  |  |  | Should |  |  | Enterprise | [15 empty] | 4.8 | The solution shall provide the ability to display the data under analysis as a space map. | Enterprise | 4 | #ERROR! | M | 1.5.7
34 |  | The solution shall have the ability to generate and display a transaction log. |  |  |  | Should |  |  | PMRS | N/A. Conceptually, these are not the kind of product that keeps a transaction log - any more than Excel does. | [14 empty] | 4.9 | The solution shall have the ability to generate and display a transaction log. | PMRS | 4 | #ERROR! | M | - | N/A. Conceptually, these are not the kind of product that keeps a transaction log - any more than Excel does.
35 |  | File Formats of Output |  |  |  | #N/A | [18 empty] | 5 | File Formats of Output |  |  | #ERROR!
36 |  | The solution shall provide the ability to export data to a Microsoft Word file. |  |  |  | Should |  |  | PMRS | Dropped. If "data" means the formatted display, then a screen shot taken with the Windows Snipping Tool does the job whether the tool provides a screen-capture feature or not. Hence, a superfluous feature. If "data" means the underlying data, nobody wants an unformatted text blob. You'd send it to Excel. | [14 empty] | 5.1 | The solution shall provide the ability to export data to a Microsoft Word file. | PMRS | 4 | #ERROR! | M | - | Dropped. If "data" means the formatted display, then a screen shot taken with the Windows Snipping Tool does the job whether the tool provides a screen-capture feature or not. Hence, a superfluous feature. If "data" means the underlying data, nobody wants an unformatted text blob. You'd send it to Excel.
37 |  | The solution shall provide the ability to export data to an Access database. |  |  |  | Should |  |  | PMRS | [15 empty] | 5.2 | The solution shall provide the ability to export data to an Access database. | PMRS | 4 | #ERROR! | M | 1.12.3 and 2.2.3
38 |  | The solution shall provide the ability to export data to an Excel spreadsheet. |  |  |  | Must |  |  | PMRS | [15 empty] | 5.3 | The solution shall provide the ability to export data to an Excel spreadsheet. | PMRS | 3 | #ERROR! | H | 1.12.4 and 2.2.4
39 |  | The solution shall provide the ability to export data in an XML-encoded form. |  |  |  | Should |  |  | PMRS | Exporting reports in XML allows for end user interactivity of dashboards, higher quality data analytics, etc. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 5.4 | The solution shall provide the ability to export data in an XML-encoded form. | PMRS | 4 | #ERROR! | M | 1.12.6 and 2.2.6 | Exporting reports in XML allows for end user interactivity of dashboards, higher quality data analytics, etc. Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
40 |  | The solution shall provide the ability to export data in an html-encoded form. |  |  |  | Must |  |  | PMRS |  | This is so that it can be displayed on an external website. | [13 empty] | 5.5 | The solution shall provide the ability to export data in an html-encoded form. | PMRS | 5 | #ERROR! | H | 1.12.7 and 2.2.7 |  |  | This is so that it can be displayed on an external website.
206 |  | The solution shall provide the ability to export data in a JSON-encoded form. |  |  |  | Should |  |  | Enterprise | [15 empty] | 5.6 | The solution shall provide the ability to export data in a JSON-encoded form. | Enterprise | 4 | #ERROR! | M | 1.12.8 and 2.2.8
42 |  | The solution shall provide the ability to export data in a PDF format. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 5.7 | The solution shall provide the ability to export data in a PDF format. | PMRS |  | #ERROR! | M |  | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
43 |  | Other Functional and Technical Requirements |  |  |  | #N/A | [18 empty] | 6 | Other Functional and Technical Requirements |  |  | #ERROR!
44 |  | The solution shall have the ability to execute multi-dimensional analytics. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.1 | The solution shall have the ability to execute multi-dimensional analytics. | PMRS | 1 | #ERROR! | H | 1.2.1 - 1.2.4
207 |  | The solution shall be able to analyze at a minimum 100 GB of data. |  |  |  | Must |  |  | Enterprise |  | (currently 5 GB in PMRS warehouse.) | [13 empty] | 6.2 | The solution shall be able to analyze at a minimum 100 GB of data. | Enterprise | 5 | #ERROR! | H | 1.10.3 |  |  | (currently 5 GB in PMRS warehouse.)
46 |  | The solution shall be accessible to users connected to NARA's internal network. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.3 | The solution shall be accessible to users connected to NARA's internal network. | PMRS | 1 | #ERROR! | H | 1.1.1
47 |  | The solution shall be accessible to NARA staff working remotely. |  |  |  | Should |  |  | PMRS |  | The solution shall be accessible through the NARA firewall for staff who work remotely. | [13 empty] | 6.4 | The solution shall be accessible to NARA staff working remotely. | PMRS | 7 | #ERROR! | M | 1.1.2 |  |  | The solution shall be accessible through the NARA firewall for staff who work remotely.
48 |  | The solution shall allow self-service use of data cubes. |  |  |  | Must |  |  | PMRS | Dropped as a separate item. All the Consumer features add up to this. And both tools do it. | [14 empty] | 6.5 | The solution shall allow self-service use of data cubes. | PMRS | 1 | #ERROR! | H | - | Dropped as a separate item. All the Consumer features add up to this. And both tools do it.
208 |  | The solution shall allow users to create their own report templates. |  |  |  | Must |  |  | Enterprise | This is Consumers saving a template based on their work. It's not creating reports de novo as analysts do. | [14 empty] | 6.6 | The solution shall allow users to create their own report templates. | Enterprise | 4 | #ERROR! | H | 1.8.4 | This is Consumers saving a template based on their work. It's not creating reports de novo as analysts do.
209 |  | The solution shall allow users to create their own visualization templates. |  |  |  | Must |  |  | Enterprise | [15 empty] | 6.7 | The solution shall allow users to create their own visualization templates. | Enterprise | 5 | #ERROR! | H | 1.8.4
51 |  | The solution shall allow users to drill down through data hierarchies. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.8 | The solution shall allow users to drill down through data hierarchies. | PMRS | 1 | #ERROR! | H | 1.2.4
52 |  | The solution shall allow users to access canned reports. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.9 | The solution shall allow users to access canned reports. | PMRS | 1 | #ERROR! | H | 3.2.1
53 |  | The solution shall allow users to visualize data in multiple ways. |  |  |  | Should |  |  | PMRS |  | heat map, treemap, scatter plot, matrix chart, network diagram, bubble chart, tag cloud, radar chart, data map, see also http://www.visual-literacy.org/periodic_table/periodic_table.html | [13 empty] | 6.10 | The solution shall allow users to visualize data in multiple ways. | PMRS | 1 | #ERROR! | M | 1.5.8 |  |  | heat map, treemap, scatter plot, matrix chart, network diagram, bubble chart, tag cloud, radar chart, data map, see also http://www.visual-literacy.org/periodic_table/periodic_table.html
54 |  | The solution shall allow users to perform ad hoc calculations. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.11 | The solution shall allow users to perform ad hoc calculations. | PMRS | 1 | #ERROR! | H | 1.4.3
55 |  | The solution shall allow users to filter data on multiple variables, data elements, or attributes. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.12 | The solution shall allow users to filter data on multiple variables, data elements, or attributes. | PMRS | 4 | #ERROR! | H | 1.3.1
56 |  | The solution shall support predictive analytics. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 6.13 | The solution shall support predictive analytics. | PMRS | 4 | #ERROR! | M | 2.4.1 | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
57 |  | The solution shall support forecasting. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 6.14 | The solution shall support forecasting. | PMRS | 4 | #ERROR! | M | 2.4.4 | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
58 |  | The solution shall provide the ability to automatically email reports to email addresses. |  |  |  | Should |  |  | PMRS | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for. | [14 empty] | 6.15 | The solution shall provide the ability to automatically email reports to email addresses. | PMRS | 4 | #ERROR! | M | 3.2.2 | Is not a current function of Databeacon but the procured BI tool 'should have' this functionality. A feature PMRS is looking for.
59 |  | The solution shall provide the ability to automatically generate reports on a user-selected periodic basis (e.g., annually, quarterly, weekly, daily, etc). |  |  |  | Should |  |  | PMRS | [15 empty] | 6.16 | The solution shall provide the ability to automatically generate reports on a user-selected periodic basis (e.g., annually, quarterly, weekly, daily, etc). | PMRS | 4 | #ERROR! | M | 3.4.2
210 |  | The solution shall provide the ability to display real-time, on-line statistics. |  |  |  | Would |  |  | Enterprise | [15 empty] | 6.17 | The solution shall provide the ability to display real-time, on-line statistics. | Enterprise | 4 | #ERROR! | L | 3.4.2
61 |  | The solution shall provide the ability to analyze and display trends in the data. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.18 | The solution shall provide the ability to analyze and display trends in the data. | PMRS | 4 | #ERROR! | H | 1.2.5
62 |  | The solution shall provide the ability to execute inferential statistical operations. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.19 | The solution shall provide the ability to execute inferential statistical operations. | PMRS | 5 | #ERROR! | H | 2.4.2
63 |  | The solution shall provide the ability to execute descriptive statistical operations. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.20 | The solution shall provide the ability to execute descriptive statistical operations. | PMRS | 5 | #ERROR! | H | 2.4.3
64 |  | The system shall allow the user to specify whether the summary displays the most recent value (stock variable) or the sum of the data for a given period (flow variable) when summarizing numeric data. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.21 | The system shall allow the user to specify whether the summary displays the most recent value (stock variable) or the sum of the data for a given period (flow variable) when summarizing numeric data. | PMRS | 5 | #ERROR! | H | 2.3.2
65 |  | The solution shall provide the ability to manage metadata to describe all entities used in an analysis. |  |  |  | Must |  |  | PMRS | [15 empty] | 6.22 | The solution shall provide the ability to manage metadata to describe all entities used in an analysis. | PMRS | 5 | #ERROR! | H | 1.9.6
66 |  | The solution shall allow users to print a visualization. |  |  |  | Should |  |  | PMRS | [15 empty] | 6.23 | The solution shall allow users to print a visualization. | PMRS | 5 | #ERROR! | M | 1.12.1 and 2.2.1
67 |  | The solution shall be capable of storing a minimum of ten (10) gigabytes of data |  |  |  | Should |  |  | PMRS | N/A. Neither of these tools is a data warehouse. They don't store data. Instead, I substituted a test of whether the tool can display the largest PMRS cube in memory. That has 3.56 million data points. | [14 empty] | 6.24 | The solution shall be capable of storing a minimum of ten (10) gigabytes of data | PMRS | 7 | #ERROR! | M | 1.10.2 | N/A. Neither of these tools is a data warehouse. They don't store data. Instead, I substituted a test of whether the tool can display the largest PMRS cube in memory. That has 3.56 million data points.
68 |  | The solution shall allow users to print a report. |  |  |  | Should |  |  | PMRS | [15 empty] | 6.25 | The solution shall allow users to print a report. | PMRS | 5 | #ERROR! | M | 1.12.1 and 2.2.1
69 |  | Compliance |  |  |  | #N/A | [18 empty] | 7 | Compliance |  |  | #ERROR!
70 |  | The solution shall comply with Section 508. |  |  |  | Must |  |  | PMRS | [15 empty] | 7.1 | The solution shall comply with Section 508. | PMRS | 5 | #ERROR! | H | 1.9.7
71 |  | The system shall comply with NARA security guidance. |  |  |  | Must |  |  | PMRS | Dropped as being a)untestable without major support from IT Secuity, and b) not likely a problem as both products are installed in dozens of government agencies. | [14 empty] | 7.2 | The system shall comply with NARA security guidance. | PMRS | 5 | #ERROR! | H | - | Dropped as being a)untestable without major support from IT Secuity, and b) not likely a problem as both products are installed in dozens of government agencies.
72 |  | The solution must meet Federal requirements for a FISMA certified solution. |  |  |  | Must |  |  | PMRS | [15 empty] | 7.3 | The solution must meet Federal requirements for a FISMA certified solution. | PMRS | 5 | #ERROR! | H | 4.2.1
73 |  | External Interface |  |  |  | #N/A | [18 empty] | 8 | External Interface |  |  | #ERROR!
211 |  | The solution shall provide the ability to analyze data from TMS Collection Management Software. |  |  |  | Should |  |  | Enterprise | TMS Runs on SQL Server. | [14 empty] | 8.1 | The solution shall provide the ability to analyze data from TMS Collection Management Software. | Enterprise | 4 | #ERROR! | M | 2.1.6 | TMS Runs on SQL Server.
212 |  | The solution shall provide the ability to analyze data from ARCIS. |  |  |  | Should |  |  | Enterprise | ARCIS Runs on Oracle. | [14 empty] | 8.2 | The solution shall provide the ability to analyze data from ARCIS. | Enterprise | 4 | #ERROR! | M | 2.1.5 | ARCIS Runs on Oracle.
213 |  | The solution shall provide the ability to analyze data from HMS. |  |  |  | Should |  |  | Enterprise | Runs on Oracle. | [14 empty] | 8.3 | The solution shall provide the ability to analyze data from HMS. | Enterprise | 6 | #ERROR! | M | 2.1.5 | Runs on Oracle.
214 |  | The solution shall provide the ability to analyze data from CMRS. |  |  |  | Should |  |  | Enterprise | Runs on Oracle. | [14 empty] | 8.4 | The solution shall provide the ability to analyze data from CMRS. | Enterprise | 4 | #ERROR! | M | 2.1.5 | Runs on Oracle.
215 |  | The solution shall provide the ability to analyze data from FPPS. |  |  |  | Should |  |  | Enterprise | Runs on Oracle. | [14 empty] | 8.5 | The solution shall provide the ability to analyze data from FPPS. | Enterprise | 4 | #ERROR! | M | 2.1.5 | Runs on Oracle.
216 |  | The solution shall provide the ability to analyze data from ADRRES. |  |  |  | Should |  |  | Enterprise | Since ADRRES is a classified system, you can't connect to it directly. It sends CSV files to PMRS. | [14 empty] | 8.6 | The solution shall provide the ability to analyze data from ADRRES. | Enterprise | 4 | #ERROR! | M | 2.1.2 | Since ADRRES is a classified system, you can't connect to it directly. It sends CSV files to PMRS.
80 |  | The solution shall provide the ability to analyze data from PMRS. |  |  |  | Must |  |  | PMRS | Runs on SQL Server. | [14 empty] | 8.7 | The solution shall provide the ability to analyze data from PMRS. | PMRS | 4 | #ERROR! | H | 2.1.6 | Runs on SQL Server.
81 |  | The solution shall provide the ability to analyze data output from Web Trends Analytics. |  |  |  | Should |  |  | N/A | N/A. Web Trends no longer used. | [14 empty] | 8.8 | The solution shall provide the ability to analyze data output from Web Trends Analytics. | N/A | 4 | #ERROR! | M | - | N/A. Web Trends no longer used.
82 |  | The solution shall provide the ability to analyze data output from Google Analytics. |  |  |  | Would |  |  | PMRS | Google analytics is gaining traction is is being used throughout NARA. There may be a requirement in the future for PMRS to connect to Google Analytics. Is not a current function of Databeacon but the procured BI tool would be 'nice to have' this functionality. | [14 empty] | 8.9 | The solution shall provide the ability to analyze data output from Google Analytics. | PMRS | 4 | #ERROR! | L | 2.1.9 | Google analytics is gaining traction is is being used throughout NARA. There may be a requirement in the future for PMRS to connect to Google Analytics. Is not a current function of Databeacon but the procured BI tool would be 'nice to have' this functionality.
217 |  | The solution shall provide the ability to analyze data from VISTA ticketing and projection software. |  |  |  | Would |  |  | Enterprise | N/A. Vista was replaced by VSS. It's reporting uses MongoDB. | [14 empty] | 8.10 | The solution shall provide the ability to analyze data from VISTA ticketing and projection software. | Enterprise | 4 | #ERROR! | L | - | N/A. Vista was replaced by VSS. It's reporting uses MongoDB.
218 |  | The solution shall provide the ability to analyze data from DAS. |  |  |  | Should |  |  | Enterprise | [15 empty] | 8.11 | The solution shall provide the ability to analyze data from DAS. | Enterprise | 5 | #ERROR! | M | 2.1.5
219 |  | The solution shall provide the ability to analyze data from OPA. |  |  |  | Should |  |  | Enterprise | OPA is now called NAC. It's built on MySQL. | [14 empty] | 8.12 | The solution shall provide the ability to analyze data from OPA. | Enterprise | 5 | #ERROR! | M | 2.1.8 | OPA is now called NAC. It's built on MySQL.
220 |  | The solution shall provide the ability to analyze data from the following ERA instances: Base, EOP, CRI, and Census. |  |  |  | Should |  |  | Enterprise | PostgreSQL now, Elasticsearch in the future. | [14 empty] | 8.13 | The solution shall provide the ability to analyze data from the following ERA instances: Base, EOP, CRI, and Census. | Enterprise | 5 | #ERROR! | M | 2.1.7 and 2.1.11 | PostgreSQL now, Elasticsearch in the future.
221 |  | The solution shall provide the ability to analyze data gathered by Splunk. |  |  |  | Should |  |  | Enterprise | [15 empty] | 8.14 | The solution shall provide the ability to analyze data gathered by Splunk. | Enterprise |  | #ERROR! | M | 2.1.10
222 |  | The solution shall provide the ability to analyze data from the Visitor Services System. |  |  |  | Should |  |  | Enterprise | VSS uses MongoDB BI. | [14 empty] | 8.15 | The solution shall provide the ability to analyze data from the Visitor Services System. | Enterprise | 4 | #ERROR! | M | 2.1.14 | VSS uses MongoDB BI.
89 |  | The solution shall support an API for the ingest and integration of external data sources. |  |  |  | Must |  |  | PMRS | API support for connectivity to cloud based solutions is critical for a modern BI tool. Is not a current function of Databeacon but the procured BI tool 'must have' this functionality. A feature PMRS is looking for. | [14 empty] | 8.16 | The solution shall support an API for the ingest and integration of external data sources. | PMRS |  | #ERROR! | H | 2.1.13 | API support for connectivity to cloud based solutions is critical for a modern BI tool. Is not a current function of Databeacon but the procured BI tool 'must have' this functionality. A feature PMRS is looking for.
90 |  | Support & Maintenance |  |  |  | #N/A | [18 empty] | 9 | Support & Maintenance |  |  | #ERROR!
91 |  | The solution provider shall install, configure, patch, provide timely upgrades as required, and support as specified in the Service Level Agreements of the contract. |  |  |  | Must |  |  | PMRS | N/A. Applies only to Software as a Service (SaaS), which is not the case with these particular tools. | [14 empty] | 9.1 | The solution provider shall install, configure, patch, provide timely upgrades as required, and support as specified in the Service Level Agreements of the contract. | PMRS | 7 | #ERROR! | H | - | N/A. Applies only to Software as a Service (SaaS), which is not the case with these particular tools.
92 |  | Backup & Recovery |  |  |  | #N/A | [18 empty] | 10 | Backup & Recovery |  |  | #ERROR!
93 |  | The solution shall provide the capability for backup and recovery of the system. |  |  |  | Must |  |  | PMRS | Collapsed into one item so as not to give undue weight to backup and recovery. | [14 empty] | 10.1 | The solution shall provide the capability for backup and recovery of the system. | PMRS | 7 | #ERROR! | H | 4.1.1 | Collapsed into one item so as not to give undue weight to backup and recovery.
94 |  | The solution shall provide the capability for the backup of application files. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.2 | The solution shall provide the capability for the backup of application files. | PMRS | 7 | #ERROR! | H | 4.1.1
95 |  | The solution shall provide the capability for the backup of database files. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.3 | The solution shall provide the capability for the backup of database files. | PMRS | 7 | #ERROR! | H | 4.1.1
96 |  | The solution shall provide the capability to schedule nightly incremental backups. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.4 | The solution shall provide the capability to schedule nightly incremental backups. | PMRS | 7 | #ERROR! | H | 4.1.1
97 |  | The solution shall provide the capability to schedule weekly full backups. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.5 | The solution shall provide the capability to schedule weekly full backups. | PMRS | 7 | #ERROR! | H | 4.1.1
98 |  | The solution shall provide the capability to manually perform a backup. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.6 | The solution shall provide the capability to manually perform a backup. | PMRS | 7 | #ERROR! | H | 4.1.1
99 |  | The solution shall provide the capability to cancel a scheduled backup process. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.7 | The solution shall provide the capability to cancel a scheduled backup process. | PMRS | 7 | #ERROR! | H | 4.1.1
100 |  | The solution shall provide the capability to cancel a manual backup process. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.8 | The solution shall provide the capability to cancel a manual backup process. | PMRS | 7 | #ERROR! | H | 4.1.1
101 |  | The solution shall provide the capability to recover application files to restore operational capability. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.9 | The solution shall provide the capability to recover application files to restore operational capability. | PMRS | 7 | #ERROR! | H | 4.1.1
102 |  | The solution shall provide the capability to recover database files to restore operational capability. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.10 | The solution shall provide the capability to recover database files to restore operational capability. | PMRS | 7 | #ERROR! | H | 4.1.1
103 |  | The solution shall provide the capability to recover from a hardware failure. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.11 | The solution shall provide the capability to recover from a hardware failure. | PMRS | 7 | #ERROR! | H | 4.1.1
104 |  | The solution shall provide the capability to recover from a physical site outage. |  |  |  | Must |  |  | PMRS | [15 empty] | 10.12 | The solution shall provide the capability to recover from a physical site outage. | PMRS | 7 | #ERROR! | H | 4.1.1
105 |  | Availability |  |  |  | #N/A | [18 empty] | 11 | Availability |  |  | #ERROR!
106 |  | The solution shall be 99% available 24 hours a day, 7 days a week. |  |  |  | Should |  |  | PMRS | N/A. Applies mainly to SaaS. For software at NARA, this is a function of NARANET and server uptime, which is not a product attribute. | [14 empty] | 11.1 | The solution shall be 99% available 24 hours a day, 7 days a week. | PMRS | 7 | #ERROR! | M | - | N/A. Applies mainly to SaaS. For software at NARA, this is a function of NARANET and server uptime, which is not a product attribute.
107 |  | Performance |  |  |  | #N/A | [18 empty] | 12 | Performance |  | 7 | #ERROR!
223 |  | The solution shall provide the capability to begin ingesting data from external systems in less than 15 seconds. |  |  |  | Should |  |  | Enterprise | [15 empty] | 12.1 | The solution shall provide the capability to begin ingesting data from external systems in less than 15 seconds. | Enterprise | 7 | #ERROR! | M | 3.4.3
109 |  | The solution shall begin generating an automated report within 20 seconds after execution. |  |  |  | Should |  |  | PMRS | [15 empty] | 12.2 | The solution shall begin generating an automated report within 20 seconds after execution. | PMRS | 7 | #ERROR! | M | 1.10.1
110 |  | Information Management |  |  |  | #N/A | [18 empty] | 13 | Information Management |  |  | #ERROR!
111 |  | The solution shall accept user-specified, periodic updates from data sources. |  |  |  | Must |  |  | PMRS | I collapsed all these system-specific details on the grounds that once the tools can connect to sources (evaluated in Section 8), its update features apply equally to all. | [14 empty] | 13.1 | The solution shall accept user-specified, periodic updates from data sources. | PMRS | 1 | #ERROR! | H | 2.1 | I collapsed all these system-specific details on the grounds that once the tools can connect to sources (evaluated in Section 8), its update features apply equally to all.
224 |  | The solution shall accept user-specified, periodic data updates from the ARCIS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.1 | The solution shall accept user-specified, periodic data updates from the ARCIS system. | Enterprise | 7 | #ERROR! | M | 2.1
225 |  | The solution shall accept user-specified, periodic data updates from the HMS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.2 | The solution shall accept user-specified, periodic data updates from the HMS system. | Enterprise | 7 | #ERROR! | M | 2.1
226 |  | The solution shall accept user-specified, periodic data updates from the CMRS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.3 | The solution shall accept user-specified, periodic data updates from the CMRS system. | Enterprise | 7 | #ERROR! | M | 2.1
227 |  | The solution shall accept user-specified, periodic data updates from the FPPS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.4 | The solution shall accept user-specified, periodic data updates from the FPPS system. | Enterprise | 7 | #ERROR! | M | 2.1
228 |  | The solution shall accept user-specified, periodic data updates from the ADRRES Base system. |  |  |  | Should |  |  | Enterprise | Since ADRRES is a classified system, you can't connect to it directly. It sends CSV files to PMRS. | [14 empty] | 13.1.5 | The solution shall accept user-specified, periodic data updates from the ADRRES Base system. | Enterprise | 7 | #ERROR! | M | 2.1 | Since ADRRES is a classified system, you can't connect to it directly. It sends CSV files to PMRS.
117 |  | The solution shall accept user-specified, periodic data updates from the PMRS system. |  |  |  | Should |  |  | PMRS | [15 empty] | 13.1.6 | The solution shall accept user-specified, periodic data updates from the PMRS system. | PMRS | 7 | #ERROR! | M | 2.1
229 |  | The solution shall accept user-specified, periodic data updates from the DAS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.7 | The solution shall accept user-specified, periodic data updates from the DAS system. | Enterprise | 7 | #ERROR! | M | 2.1
119 |  | The solution shall accept user-specified, periodic data updates from the Web Trends Analytics system. |  |  |  | Should |  |  | N/A | Web Trends not being used. N/A | [14 empty] | 13.1.8 | The solution shall accept user-specified, periodic data updates from the Web Trends Analytics system. | N/A | 7 | #ERROR! | M | 2.1 | Web Trends not being used. N/A
230 |  | The solution shall accept user-specified, periodic data updates from the Google Analytics system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.9 | The solution shall accept user-specified, periodic data updates from the Google Analytics system. | Enterprise | 7 | #ERROR! | M | 2.1
231 |  | The solution shall accept user-specified, periodic data updates from the VSS system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.10 | The solution shall accept user-specified, periodic data updates from the VSS system. | Enterprise | 7 | #ERROR! | M | 2.1
232 |  | The solution shall accept user-specified, periodic data updates from the OPA PROD system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.11 | The solution shall accept user-specified, periodic data updates from the OPA PROD system. | Enterprise | 7 | #ERROR! | M | 2.1
233 |  | The solution shall accept user-specified, periodic data updates from the ERA Base system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.12 | The solution shall accept user-specified, periodic data updates from the ERA Base system. | Enterprise | 7 | #ERROR! | M | 2.1
234 |  | The solution shall accept user-specified, periodic data updates from the ERA Census system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.13 | The solution shall accept user-specified, periodic data updates from the ERA Census system. | Enterprise | 7 | #ERROR! | M | 2.1
235 |  | The solution shall accept user-specified, periodic data updates from the ERA CRI system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.14 | The solution shall accept user-specified, periodic data updates from the ERA CRI system. | Enterprise | 7 | #ERROR! | M | 2.1
236 |  | The solution shall accept user-specified, periodic data updates from the ERA EOP system. |  |  |  | Should |  |  | Enterprise | [15 empty] | 13.1.15 | The solution shall accept user-specified, periodic data updates from the ERA EOP system. | Enterprise | 7 | #ERROR! | M | 2.1
237 |  | The solution shall provide the ability to perform global updates using data from all data sources at the same time. |  |  |  | Must |  |  | Enterprise | [15 empty] | 13.2 | The solution shall provide the ability to perform global updates using data from all data sources at the same time. | Enterprise | 5 | #ERROR! | H | 3.4.1
128 |  | The solution shall provide the ability to perform updates using data from a single data source. |  |  |  | Must |  |  | PMRS | [15 empty] | 13.3 | The solution shall provide the ability to perform updates using data from a single data source. | PMRS | 5 | #ERROR! | H | 3.4.1
129 |  | The solution shall provide the ability to perform updates to single entities from a single data source. |  |  |  | Must |  |  | PMRS | [15 empty] | 13.4 | The solution shall provide the ability to perform updates to single entities from a single data source. | PMRS | 5 | #ERROR! | H | 3.4.1
130 |  | Training Requirement |  |  |  | #N/A |  |  | PMRS | [15 empty] | 14 | Training Requirement |  |  | #ERROR!
131 |  | The solution shall provide online training at different levels based on the competency of the user. |  |  |  | Should |  |  | PMRS |  | This training will be available to any user of the system at no cost. | [13 empty] | 14.1 | The solution shall provide online training at different levels based on the competency of the user. | PMRS | 7 | #ERROR! | M | 1.9.5 and 2.5.5 |  |  | This training will be available to any user of the system at no cost.
132 | 1 | The consumer can display certain measures and hide others. | [6 empty] | PMRS | Many PMRS cubes show lots of measures - # of, % of, holdings in cu.ft., holdings in pages, start-of-year holdings, and so on. The consumer often wants to hide the measures that don't interest him at the moment, the better to de-clutter the view. | [18 empty] | #ERROR!
133 | 3 | The consumer can display two or more measures simultaneously. | [6 empty] | PMRS | Sometimes uses want to compare measures in a display, such as a seeing the number of respondents to a survey, the number of happy respondents, and the % happy. The tool should support this.
134 | 5 | The user can see the values of data points on graphical displays, typically by mousing over the point. | [6 empty] | PMRS | This is a minor feature. When looking at a graphical display, it lets users inspect the data values underneath an object by mousing over it.
135 | 7 | The consumer can swap between text and graphical displays of the same data without the publisher having pre-designed each display. | [6 empty] | PMRS | With Databeacon, the user can start with a table, click a button, and see a bar chart, all self-serve. By contrast, with Tableau, if you start with a text display, no charts are available unless the Publisher has created them. This design greatly increases the parts count for the Publisher.
136 | 9 | The consumer can swap between types of graphical displays without the publisher having pre-designed each display. | [6 empty] | PMRS | Likewise, we want users to be able to flip between bar, pie, and line charts without the Publisher having to have separately created each one.
137 | 11 | Undo – The consumer displays have a step-wise undo feature (usually an undo button). | [6 empty] | PMRS | This is an obvious requirement.
138 | 13 | The consumer can export a display as a PDF file. | [6 empty] | PMRS | I'm sure there will be a demand for PDFs.
139 | 15 | The tool can import data from Access. | [6 empty] | Enterprise | Even though NARA is downplaying Access, there are still a lot of Access data sources. Currently, Access database data gets ingested through Oracle Data Integrator. Not a PMRS requirement.
140 | 17 | Undo – The analyst displays have a step-wise undo feature (usually an undo button). | [6 empty] | PMRS
141 | 19 | The analyst can export a display as a PDF file. | [6 empty] | PMRS
142 | 21 | The tool can aggregate values up a hierarchical dimension. For example, if given monthly data, it can calculate the quarterly and yearly totals. | [6 empty] | PMRS | It's not enough to drill in and out. We want the tool to calculate sums correctly when we do.
143 | 23 | The tool supports fiscal years natively. | [6 empty] | PMRS | NARA uses fiscal years in hundreds of reports. These need to be supported without workarounds or programming.
144 | 25 | Isolation - The tool has a way to keep each of NARA’s various publishers separate, such that each has no access to the others’ data or work products. | [6 empty] | Enterprise | THIS IS ABSOLUTELY CRITICAL. This is critical if leveraged as a enterprise solution, not a targeted PMRS solution
145 | 27 | Displays can be published with their data embedded so that they run entirely in memory with no need to re-query the source database. | [6 empty] | PMRS | We want an in-memory product because they run faster and our (PMRS) data is small.
146 | 29 | Displays can be published so that they do re-query their source database on execution. | [6 empty] | PMRS | But we want this, too, for when the data in the display is just too big for memory.
147 | 31 | User groups – The Publisher can identify named users and create groups of users. This feature is necessary to create user-specific dashboards. | [6 empty] | Enterprise | If we want more than one generic dashboard, then the publisher needs to know about groups and the people who belong in them.
148 | 33 | Integration with Active Directory – The tool will identify users via Active Directory. | [6 empty] | Enterprise | Then, if you need to know about people, you need single sign-on, which means Active Directory.
149 | 35 | Anonymous users – The tool supports use by anonymous users. (Thus, the administrator does not need to maintain a list of all users, just those with non-default dashboards.) | [6 empty] | PMRS | Conversely, we don't want the Publishers to have to maintain user lists when most users don't need special treatment, and hence can be anonymous.
150 | 37 | During the evaluation, the vendor’s support was readily available and competent. | [6 empty] | PMRS | This is a proxy for the kind of customer support we can expect in the future.
151 | 39 | The product has an online community forum ready to answer questions. | [6 empty] | PMRS | This kind of support enormously eases implementation and ongoing work.
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206

## StandardValues
Type | Category | Priority |  | Status | Verification Method | Verification Status | UAT Status
Business | Functional | Must | Requirements that are CRITICAL to meeting the project's objectives | Approved | Inspection | Pass | Pass
Stakeholder | Non-Functional | Should | Requirements that are critical and should be included if possible, but which can be excluded | Deferred | Analysis | Fail | Fail
System | Constraint | Could | Requirements that are part of the project's scope and add or enhance project benefits | Draft | Test | N/A | N/A
| N/A | Would | Requirements that do not have a significant impact on project benefits or could be considered as a “would like to have” | Obsolete | Demonstration
Certification
N/A